## Sheet1
PROJECT CLOSEOUT TURNOVER CHECKLIST (Revised April 23 2020)
Project Name: | SHO Lobby and Conference Center
Regeneron Project Manager(s): | Lysander Chan
Construction Management Firm:
CM Contact, Phone, E-mail:
Architecture/Engineering Firm: | FCA / Vanderweil
A/E Contact, Phone, E-mail: | Denis Kovalich, 215-255-7225, Dkovalich@fcarchitects.com
Initial Regn. PM Review (name & date): | Lysander Chan
Initial Regn. Eng. Review (name & date):
Date CM Turned-Over Closeout for Review:
Final Regn. PM Approval (name & date):
Categories |  | To be Submitted By | Date Submitted | Regeneron Confirmed (Initials)
Design Docs (upload to SharePoint folder structure) (Individual PDF sheets and a PDF of all sheets combined in one or more files)
Permit Set(s) (PDFs) |  | FCA
Consolidated Set of all disciplines required below (CAD & PDFs) *(see notes 1 & 8 below) |  | FCA
Design Record Drawings for all disciplines checked below *(see notes 2 & 8 below) |  | FCA
Architectural (CAD and PDFs) |  | FCA
Structural (CAD and PDFs) |  | FCA
Mechanical (CAD and PDFs) |  | FCA
Electrical (CAD and PDFs) |  | FCA
Plumbing (CAD and PDFs) |  | FCA
Fire Alarm (CAD and PDFs) |  | FCA
Fire Suppression (CAD and PDFs) (FP/SpriFCAler) |  | FCA
Structured Cabling (CAD and PDFs) (Tel-Data) |  | FCA
Audio-Visual (CAD and PDFs) |  | Reg
Security (CAD and PDFs) |  | Reg
Survey (CAD and PDFs) |  | N/A
Geotechnical (CAD and PDFs) |  | N/A
Civil (CAD and PDFs) |  | N/A
Landscape (CAD and PDFs) |  | N/A
Distributed Antenna Systems (CAD and PDFs) |  | Reg
Other (CAD and PDFs) |  | FCA
Project Manual-Specifications |  | FCA
Revit Files and LiFCAed Files (CAD, image files, and excel files) |  | FCA
Construction (upload to SharePoint folder structure)
Submittals (All approved and product data, named and organized by CSI Masterformat Divisions)
Submittal Log |  | GC
RFI Log |  | GC
Testing Reports
Air & Hydronic Test and Balance Reports |  | GC
Electrical Short Circuit Analysis and Arc Flash Study (Electical Inspection Sign Uploaded) |  | GC
Environmental Remediation, Preconstruction (ACP5/ACP7/Asbestos Survey) |  | Reg
Equipment Factory Acceptance Testing |  | GC
Equipment Start Up Reports |  | GC
Exterior Envelope Testing Reports |  | N/A
Fire Life Safety Testing Report (device testing, audibility) |  | GC
Other Testing Reports Required (List here: |  | GC
Roof Repairs/Reports |  | GC
Soil Reports |  | N/A
Waterproofing Reports |  | N/A
Permits (Original)
Building, Plumbing, Electrical, etc. Permits (Highlight or list required permits here) |  | GC
Elevator Permit or Acceptance Letter |  | GC
Environmental Permits (Air, Emissions, Waste, Other) |  | GC
Punch List (completed and signed) |  | GC
Cert. of Final Completion |  | GC
Certificate of Occupancy (TCO has been Uploaded) |  | GC
Contractor As-builts (organized by CSI Masterformat 50 Divisions)
00-As-Built Red-lined Design Drawings (PDFs) *(see note 3 below)
Architectural Floor Plans (Markup any changes to dimensions or layout) |  | FCA
Architectural RCP's (Markup any changes to dimensions, layout, finishes, MEP items, and tags) |  | FCA
Architectural Finish Plans and Schedules (Markup any changes to tags or schedules) |  | FCA
Electrical Panel Schedules and Riser Diagrams (Markup any changes to schedules or risers) |  | FCA
Mechanical Air Flow Diagrams (Water Flow Diagrams & Schedules: Markup any changes) |  | FCA
Plumbing Riser Diagrams & Schedules (Markup any changes) |  | FCA
05-Structural Steel *(See note 8 below)
3D CAD or BIM Files |  | FCA
As-built PDFs and 2D CAD or DWF Files |  | FCA
08-Curtain Wall, Window Wall, Storefront *(See note 8 below)
3D CAD or BIM Files |  | FCA
As-built PDFs and 2D CAD or DWF Files |  | FCA
21-SpriFCAler (FP) *(See note 8 below)
3D CAD or BIM Files |  | FCA
As-built PDFs and 2D CAD or DWF Files |  | FCA
22-Plumbing *(See note 8 below)
3D CAD or BIM Files |  | FCA
As-built PDFs and 2D CAD or DWF Files |  | FCA
23-HVAC *(See note 8 below)
3D CAD or BIM Files |  | FCA
As-built PDFs and 2D CAD or DWF Files |  | FCA
25-BMS *(See note 8 below)
As-built PDFs and 2D CAD or DWF Files
26-Electrical *(See note 8 below)
3D CAD or BIM Files |  | FCA
As-built PDFs and 2D CAD or DWF Files |  | FCA
26 09-Electrical and Lighting Controls *(See note 8 below)
As-built PDFs and 2D CAD or DWF Files |  | FCA
27 10-Structured Cabling (Telecom/Data) *(See note 8 below)
As-built PDFs and 2D CAD or DWF Files |  | FCA
As-built Structured Cabling Pull List (Excel file in format as specified by Regeneron) |  | FCA
27 50-DAS / DOT *(See note 8 below)
As-built PDFs and 2D CAD or DWF Files |  | FCA
28 40-Fire Alarm Riser Diagram *(See note 8 below)
As-built PDFs and 2D CAD or DWF Files |  | FCA
List of Attic Stock (List of products, quanitities, and location of stock) |  | GC
Operations & Maintenance Manuals |  | FCA
Warranties
Manufacturer Warranties |  | GC
Workmanship Warranty Letters-Trades (for all trades, including effective date) |  | GC
Service Agreements (major equipment) |  | GC
Commissioning (upload to SharePoint folder structure)
Building Equipment and Building System Lists *(see note 4 below) |  | GC
Prefunctional Checklist |  | GC
Functional Performance Test |  | GC
Final Report |  | GC
Project Turnover Checklist (upload to SharePoint folder structure)
Project Closeout Turnover Checklist (completed and signed off by Regn - this document) |  | Reg
Equipment Ownership Matrix (by Regeneron, *see note 5 below)
BIM PxP (upload to SharePoint folder structure)
BIM Project Execution Plan |  | N/A
Project Team Info (upload to SharePoint folder structure)
Design Team Directory *(see note 6 below) |  | Reg
Vendor and Subcontractor Directory *(see note 7 below) |  | GC
Financials + Contracts (sent via email to Regeneron Project Manager. Do not upload to SharePoint)
Affadavit of Total Project Cost (Final) |  | GC
Copies of all CM trade backups; (bills, invoices, payments, and statements covering project cost) |  | GC
Final Lien Waivers |  | GC
Other Required Turnover Items: (List here if any
Notes: 1) The "Consolidated Set" is the most current version of each drawing/spec/file at the completion of construction. Must include an updated drawing list which indicates each revision along with the date of the revisions. 2) The "Record Set" is the set of Construction Documents amended by the Design Team to match As-Built conditions as per information provided by the Contractor in the As-Built documents. "Record Set" along with the date should appear in the title block. 3) The "As-built Red-lined Design Drawings" are markups maintained by the Contractor(s) that document where installed conditions deviate from the Consolidated Drawing Set prepared by the design team. If no changes were made, add "As-built" to the relevant construction drawings. These drawings must be given to the design team before the project is complete so their Record Drawings can be updated, if needed. 4) The "Building Equipment and Building System Lists" in the Commissioning section are lists prepared by the Contractor for use by the Commissioning Agent. 5) The "Equipment Ownership Matrix" is prepared by Regeneron to differentiate which building systems equipment is to be managed by Regeneron staff (typically systems which serve the Vivarium) and which is to be managed by the managing company (e.g. JLL). 6) Inclusive of primary design consultants [civil, architectural, structural, mechanical, electrical, plumbing], sub-consultants, and other design service providers involved in the project. 7) Inclusive of vendors, subcontractors, or other suppliers of materials, equipment, and systems involved in the project. 8) The following are Regeneron requirements for preparing and sending CAD and BIM files to Regeneron for project closeout. - Follow all requirements in Regeneron's Digital Deliverable Requirements. - Detach all unecessary xrefs, images and other reference files from the files. - Include all necessary xrefs, images and other reference files in the same folder as the CAD or BIM file, or use xref "bind", "insert" instead. We highly recommend the etransmit command for this process. - All unused objects and artifacts should be cleaned up or removed from the drawings. A purge and an audit are also recommended. - For contractor CAD files, “As-Built” along with the date should appear on the title block. The CAD files must contain all annotation that was used to generate the submittals. - For A/E record drawings, “Record Set” should appear on the title block along with the date. - The original file format used to prepare the drawings is a required deliverable, cleaned up as noted above (xrefs, purge, audit). - For files that are not 2D Autocad 2013 dwgs, or that were created using an AutoCAD vertical such as AutoCAD MEP, save a second version in Autocad 2013 with the proxygraphics set to 1 instead of 0 with “2013” added to the end of the file name so we can easily identify the down-saved version. The "dwgconvert" and "-saveasautocad" command maybe helpful with down-saving. Flatten all 3D objects. All elements shall have a "Z" coordinate of 0. - For files that cannot be converted to a "clean" 2 dimensional AutoCAD file, print DWF files from Model Space that encompass the entire extent of the drawing at 1:1 scale. - Include a transmittal that lists each file and exactly which software and version was used to create it. For example, “3G Ductwork.dwg – Autocad MEP 2019”. Include this transmittal in the same folder with the CAD files. -When exporting DWG’s from Revit, please use the DWG/DXF export setup from the Regeneron resource file. This will automatically export revit elements to our layers, along with settings for other Regeneron requirements. The resource file will be provided upon request. Export all 1/4"=1'-0" and 1/8"=1'-0" floor plans and ceiling plans from a view (not a sheet) that encompasses the entire (not partial) floor and includes the Regeneron Origin Point family and all annotation relevant to that view.