## Structural Steel & Misc. Metals
| Structural Steel & Misc. Metals |  | Sub Name/Contact:
| Regeneron TT CX Childcare Facility |  | CONSIGLI
CONTRACT DOCUMENTS
Drawings prepared by: Gensler dated 5.20.2022
Specifications prepared by: Gensler dated 5.20.2022 including:
Section 05 12 00 - Structural Steel Framing
Section 05 20 00 - Steel Joists
Section 05 30 00 - Steel Decking
Section 05 51 19 - Metal Grating Stairs
Section 05 52 13 - Pipe and Tube Railings
Addenda prepared by: Gensler
Addendum __ dated __________
Compliance with all Division 0 and 1 specifications as applicable.
X |  | Compliance with Owner's contract
X |  | Compliance with Consigli contract
Consigli Supplemental Attachment A - Schedule
Consigli Supplemental Attachment B - Logistics Plan
Consigli Supplemental Attachment C - Lean Requirements
Consigli Supplemental Attachment D - Quality Plan
Consigli Supplemental Attachment E - Textura Construction Payment Management System Information
Consigli Supplemental Attachment F - Project Safety Requirements
Consigli Supplemental Attachment G - 3D Coordination Specification (as applicable to this trade)
Consigli Supplemental Attachment H - COVID-19 Site Specific Safety Plan
Consigli Supplemental Attachment J - Zero Tolerance for Harassment or Bias
SCOPE OF WORK
GENERAL
Provide all labor, materials, and equipment as required to complete the scope of work as shown on the drawings, and as further described below.
Specific items identified below are intended as a reference for scope only. Subcontractor is responsible for providing all items for their work and related work shown on the drawings, as specified, or needed to make this scope of work complete.
Inclusion of all reference keynotes and general notes shown on drawings, as applicable to this trade.
| 051200 | Structural Steel (Furnish & Install)
Includes all structural steel for columns, beams, parapet supports, connections, etc. as shown & specified.
Includes relieving angles as shown & specified
All roof frames per structural/MEP drawings
Includes all steel for canopies / overhangs
| S520 | Includes all steel for roof screens
| 5/S520 | Includes all stiffeners under screen wall posts
Includes all steel for roof dunnage
| 1/S150 | Includes all steel for low roof
| 4/S150 | Includes all steel for lobby vestibule
Includes beam penetrations as shown on drawings, as shop fabricated
Reinforcing of horizontal penetrations through structural steel
Includes all kicker braces as shown.
Includes all welded tube framing & welded angle as shown
Includes all stiffeners
| 5/S502 | Includes all steel for sloped roof systems
Includes all brace frames & moment connections as shown
Includes all shear connections
Includes all structural steel connections
Includes all primed & painted steel as shown & specified.
Includes exposed structural steel to be galvanized as specified
| 052000 | Steel Joists (Furnish & Install)
Includes all steel joists as shown & specified
Includes all connections
Includes all joist reinforcement
Includes all stiffeners as required
Includes all bridging as required
| 4/S502 & 1/S503 | Includes WT beam connections at WF beams where joists are perpendicular
| 053000 | Steel Decking (Furnish & Install)
Includes all metal roof decking as shown & specified
Includes all deck closure plates
Includes all bent plates as shown.
Includes all shear studs as required
Includes all reinforcement at openings through metal deck
| 6/S502 | Includes plates to extend deck flutes as required
Connections to CFMF Structure
Includes all steel, connections, fasteners, welding, etc. as shown & specified for attachment of structural steel, joists, and decking to CFMF shear and bearing walls
| 2/S503 | Includes all joist bridging to shear and bearing wall connections
| 1/S600 | Includes all bridging between joists to allow for metal deck attachment and shear transfer from diaphram to walls below
Erection (Provide Breakout value $$)
Includes crane for hoisting including all fees & permits
Includes working off control lines by GC
Includes gas powered welders if required prior to temp power being set up
Includes crane inspections & certifications prior to start of erection
All erection plans
NAME OF PROPOSED ERECTOR
Shop drawings & engineering
Provide delegated design, in accordance with specification and general notes, including:
Metal stair structures (where provided by this contractor)
Pipe and tube railings
All connection details
All structural calculations by qualified engineer registered in state of project
All detailed drawings
All other submittals per spec section
Furnished items only (to be installed by Others):
Furnish all anchor bolts
Furnish all anchor bolt templates
Furnish all loose bearing plates (all bearing plates to have 3/16" holes for attachment to wood forms)
Furnish all embeds (provision for holes if required for attachment to wood)
Furnish all bolts & anchors for connections
| 3/S301 | Furnish structural plate and tension fasteners for shear wall strap base embedded in concrete. Provide all welding as shown
Lintels
Supports for millwork/finish carpentry (excluding pre-manufactured support systems)
Metal Fabrications
Includes all metal pan stairs, landings, nosing's, stringers, railings, balusters, guardrails etc. as shown & specified.
Metal equipment stairs, gratings & platforms as shown & specified
Exterior railings at stair and roof
Miscellaneous shelf angles
Shop primers as specified for all items specified
Touch up of all shop finishes
Ornamental/Decorative Metals
Furnish & install all decorative/ornamental metals as shown & specified
| 04/A407 | Stainless steel ballet bars - Movement Matters Zone
Miscellaneous
Visited site
Includes riggers liability insurance in the amount of $1M
Includes anchor bolt survey
Include all permits, licenses & fees required for the work of this trade
Include all AESS as shown & specified
Touch up painting/priming
Includes hand-setting of steel as required.
All testing as specified & required
Include all guying/shoring as required
Temporary cable rails at perimeters of all levels (3 rail turnbuckle system)
Temporary cable rails at floor/roof openings (3 rail turnbuckle system)
Maintenance of cable rails while on site
Compliance with all AISC standards
AISC certified fabricator (Yes or No?)
| 051200 - 1.5E | AISC certified erector (Yes or No?)
Installation per tolerances of specifications
All tie offs & safety protocols while erecting steel
Connections with stamped drawings by certified Structural Engineer for stairs & railings
Installation per tolerances of specifications
Seismic/vibration requirements
3D Shop drawings
BIM Coordination
Mockups as shown/specified
Clean up to dumpster (dumpsters provided by Consigli)
QUANTITIES
Manhours
Average number of workers on site
Tons of Structural Steel
Roof Decking
Roof opening frames
Moment connections
BREAKOUT VALUES ($$ - included in values above)
Erection
Detailing & Engineering
Capital improvement sales tax (tax on materials)
ADDITIONAL PROJECT-SPECIFIC REQUIREMENTS
Capital improvement sales tax (tax on materials)
All manufacturers, materials and finishes as shown and specified.
Includes performance and quality requirements as specified.
X |  | Includes all submittals, shop drawings, warranties, etc. as specified and required.
X |  | Layout from control provided by GC.
X |  | Includes all field measurements as required.
All hoisting and rigging of equipment and materials as required to complete the work of this Subcontract.
All equipment including staging/ladders/lifts etc. as required to complete the work of this trade.
Any additional electrical requirements in order to perform own work including task lighting, special power requirements, generator, etc. The electrical contractor shall provided temporary construction lighting and power within OSHA standards
X |  | Includes protection of all materials/equipment supplied by this subcontractor, stored on site.
All protection of adjacent work surfaces as required and repair of adjacent surfaces if damaged or disturbed during own work
X |  | 6'0" fall protection.
Provisions for off-hour work as required.
Temp. shutdowns of existing systems (work arounds), as required for completion of the work of this trade, Including off-hours work (if applicable).
X |  | Inclusion of all materials & labor price increases for the duration of the project.
Inclusion of any and all tariffs in place, and known about, as applicable, at the time of a signed contract agreement.
Includes LEED requirements as specified.
X |  | All offsite storage costs required for the completion of work of this trade.
Complete work of this trade as shown on all contract documents including A's, S's, MEP's etc.
All permits, licenses and fees as required to complete all work of this trade
This subcontractor shall be responsible for clean-up of trash and debris to CM provided dumpsters on a daily basis as well as sorting and separating of waste for recycling
Provisions for compliance with all Codes, Rules and Regulations
Complete work in accordance with OSHA Regulations (OSHA 10 training for all installers)
Mandatory attendance at pre-construction meeting (2) weeks prior to start of project
Subcontractor has included all cost required to conform with the CCC COVID-19 site-specific safety plan including, but not limited to, manpower and crew modifications, PPE requirements, testing requirements etc., in order to stay in strict compliance while performing all work on site.
All trades are responsible for providing their own penetrations, coring, cutting, sleeves, etc. regardless of size or location. This subcontract is responsible for sealing their own penetrations matching the requirement for fire / smoke ratings of wall / ceiling / floor being penetrated
Provide any required shoring or bracing in order to complete own work. Subcontractor shall retain the services of a professional engineer to design and supervise the installation of any required underpinning, shoring, bracing, etc. if required to complete the scope of work
Provisions to assist Owner's 3rd party testing & inspection agency as required
Provisions to assist Owner's commissioning agent as required
All requisitions are to be done on Textura software.
EXCLUSIONS
Final adjustments of relieving angles
Installation of loose lintels & angles
Installation of anchor bolts & base plates
Removal of temporary cable rails
SCHEDULE REQUIREMENTS
Lead Times
Samples
Submittals
Shop drawings
Materials (from approval)
Schedule of work per Consigli Supplimental Attachment A - Schedule
Includes all mobilizations as required
Provisions for phasing as required
ADDITIONAL QUALIFICATIONS AND REQUIREMENTS
Contract Terms & Conditions
Review CCCI contract terms & conditions?
Agree with standard subcontract language?
Payment terms: PAY WHEN PAID, 5% retainage
Insurance Coverages and Safety
Capable of providing insurance coverages as required
General Liability: $1 mil, $2 mil general aggregate
GL aggregate limit is per project, not per policy
Riggers Liability (as applicable to trades): $1 mil
Automobile: $1 mil
Umbrella Liability as follows:
Structural Steel: $15 mil
Glass & Glazing, Fire Protection, Plumbing, HVAC, Electrical: $10 mil
All other trades: $5 mil
Worker's Comp
Professional Liability: $2 mil (for design/stamped drawings and testing scope's only)
All insurance certificates must:
Have 30 Day Notice of Cancellation Endorsement attached
Name Consigli Construction Co., Inc., Owner and any other parties as required by contract, as additional insured.
.
ALTERNATES
UNIT PRICES
Foreman billable rate (Includes OH&P)
Journeyman billable rate (Includes OH&P)
Foreman billable rate (Includes OH&P)
Journeyman billable rate (Includes OH&P)
Additional picks (per pick)
Additional structural steel (fabricated & erected per ton)
Roof opening frames (Shop/Field)
Round beam penetration (Shop/Field)
Reinforced round beam penetration (Shop/Field)
Reinforced rectangle beam penetration (Shop/Field)