## BID RFI Log
Request For Information (RFI) Log
L'Dor Assisted Living Facility
New City, NY
5.18.2021
BID RFI# | Question/ Assumption | CSI Div. | Dwg Ref | Spec Section | Date Submt'd | Answer | Answered By | Date Answered
1 | The door schedule notes door tag 112 to be hollow metal, however, elevation for Door No. 112 notes this opening as aluminum. Please confirm. | 08 - Openings | A11 | 081113 084213 | 2021-05-17 | Door tags 100 and 101 to be Aluminum medium stile, non-rated | Harris A. Sanders | 2021-05-18
2 | Please confirm 45-minute fire ratings are required at aluminum doors 100, 101 and potentially 112. | 08 - Openings | A11 | 081113 084213 | 2021-05-17 | Door tag 112 to be Hollow Metal, 45-Minute Rated on Mag Holds | Harris A. Sanders | 2021-05-18
3 | Per the geotechnical report, it is understood that unsuitable soils are present. Please provide the quanity for export of unsuitable materials and import of structural fill. | 02 - Sitework | Civil Drawing 5 | 020000 | 2021-05-18 | Include the following quantities in base bid: - Export Unsuitable Soils: 6,200 CY @ $___ CY - Import Structural Fill: 2,750 CY @ $___ CY Provide unit prices for the quantities above to be used for addition/deduction of scope of work. Please note this material will only be tracked for quantities above and beyond the base bid/design elevation and scope of work. All work associated with base design is to be included with Base Bid. | Consigli | 2021-05-18
4 | Please confirm if soil can be staged on site for work required in Phase 2. | 02 - Sitework | Civil Drawing 5 | 020000 | 2021-05-18 | Soil is allowed to be stored on site as long as it does not interfere with construction or operation of the existing facility. It is the site subcontractors responsibility to manage material storage and soil erosion measures throughout the project. | Consigli | 2021-05-18
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45