## Sheet1
Catskills Crockfords RFI's
RFI # | Question | Answer | Responsibilty
1 | We are requesting a bid extension. Please Advise. | Yes, extended until October 20th | Construction/Purchasing
2 | We are requesting a date extension for RFIs. | NA | NA
3 | Is phasing require for this project? Can we shut down all areas at once or phase through? | Price this out to do floor 1 & then all of floor 3 (high limits/butterfly bar area) | Facilities / Operations
5 | Please provide information and contact info for the following vendors: | see below | Facilities
5a | Fire Alarm | Fire alarm: Kain Rider <KRider@firesecuritysound.com> | Facilities
5b | BMS HVAC controls | BMS: Bradley Taylor 518.817.0429 bradley.1.taylor@jci.com | Facilities
5c | Security system. | N/A | Facilities
6 | What is the scope of work for the security system? Back boxes / empty conduit / pull string? | Security/surveillance scope to be provided by owner. | Architect / Jason A.
7 | We are assuming that the roof system is under warrantee. Correct? | No longer under warrentee | Facilities
8 | Please provide manufacture and the roofing contractor information. | Barrett Roofing/Kurt Ricker 203.744.2780 | Facilities
9 | We are assuming the existing structural steel is fireproof. Correct? | Yes, existing structural steel is fireproofed. | Architect
10 | For scheduling purposes, what is the delivery schedule for the owner supply carpet? | TBD | Construction
11 | Please provide egress plan from the loading dock to the areas of work. | see attached plans | Facilities (please mark plan)
12 | What precaution/protection is required to work on the pool side? Such as protection / dust control etc. | Full protection / temp wall that ties back to the current bar | Construction
13 | Who is responsible for the building permits? | Owners Responsibility
14 | It was mentioned the tax status for this project is capital improvement. Please confirm | Confirmed | Purchasing
15 | Please provide the badging procedure and requirements. | see attached | Purchasing
16 | Please confirm all gaming equipment and furniture will be removed and store by RWC. | Facilities will handle furniture | Facilities/Slot Operations
17 | Please advise on the carpet spec/pattern for coordination of install with our flooring vendor. | will send in separate email | Construction
18 | Please provide lead times for all owner purchased items. | TBD | TBD
19 | Please advise if we are to price work on straight time or all overtime? Will the space be made inactive or will it be active; this will help us determine temporary protection. | straight time | Facilities/Operations
20 | Please provide capacity and dimensions for freight elevator. | 98"L 68"W 93"H 5000LBS | Facilities
21 | Please confirm GC is not responsible for low voltage.
22 | Please advise on building vendor list; this will help us expedite the process for gaming commission. |  | Purchasing
23 | Please confirm the GC is not responsible for kitchB27:B32en equipment and if this will be done by the required kitchen vendor. Please advise if we are to include the kitchen vendor's scope of work in our bid. | Kitchen equipment, accessories, and work are to be included in GC's scope of work. | Architect / Kitchen Consultant
| 2. Please provide deck heights at the 1st and 3rd floors. | 1st floor: 14'-0" above L1 F.F.E., 3rd floor: 18'-0" above 2nd floor F.F.E.
| 3. Are shop drawings required for 11/A8? Or, do you want us to figure a certain size/gauge? | Yes, shop drawings will be required for the sliding door assembly and connection.
| 4. Please provide access plan/routes to bring materials to/from the third floor. | see attached plans
| 5. In 1/A4, at the new wall/soffit above the sliding door/track system, there is a canopy/skylight/enclosure of some sort above the pool area. Please provide more details for this area, possibly an elevation view from the pool side, including dimensions, and a scope of work, etc. | Please see Addendum No. 02 dated 09/26/2022 for more information on this assembly. Enlcosure walls of lounge extention are to terminate at 12'-9 1/2" A.F.F.; see also detail 11/A-5.
| 6. There are no drawings for first floor plumbing demolition and second floor ductwork. Please confirm or clarify this. | Please see sheet M-8 for first floor plumbing scope. No ductwork scope on second floor.
| 7. Is there any ductwork at the first floor? See drawing M-5. | No ductwork scope on first floor.
| 8. Please provide project access routes and plans (i.e. worker ingress/egress, trash removal, materials/equipment storage to installation, etc.). | see attached plans