## **Responses to comments received from the owner:**

In response to comments received from the Owner regarding Update #1, the following responses and/or changes have been made:

* **Please provide Siemens controls durations. Missing from the schedule. both schools.**  
  *Siemens has not yet provided joe Lombardo P&H, inc. the durations.*
* **Please provide insulation durations. Missing from the schedule.***All Insulation durations have been adjusted to 5% of the pipe installation duration.*
* ******RTUs on roof lead time? if they arrive before spring break. this work can be scheduled for spring break normal shift.***Activity C5960 - C7110 - C5840 - C7090 will start in the spring break 2024.*
* **Please discuss this with your sub. due to clearances, containment, etc. This could take 5 days. update schedule accordingly.***Activity C6970 has its duration changed to 5 days.*
* **floors and ceilings need to be patched before school starts. please accelerate this scope to be complete by September 5.**

*The architectural work for the lower level/basement (Barr MS) has been pulled back to start by Mid-August and finish by the end of August.*



* **Refrigerant piping above ceilings may commence second shift during school year. We have spoken to the district. They are ok with temp ceiling removals during the school year.**

*Mechanical work for the first floor (Barr MS) will start in January 2024.*

* **Update for “Install New Roof Framing for Mechanical Equipment - Roof - Barr MS” during winter break 2023.**

*Mechanical work for the roof (Barr MS) was completed in January and will show their progress on update #02.*

