## Responses to comments received from the owner:

In response to comments received from the Owner regarding Update #1, the following responses and/or changes have been made:

- Please provide Siemens controls durations. Missing from the schedule. both schools.
Siemens has not yet provided joe Lombardo P&H, inc. the durations.

- Please provide insulation durations. Missing from the schedule.
All Insulation durations have been adjusted to 5% of the pipe installation duration.

- RTUs on roof lead time? if they arrive before spring break. this work can be scheduled for spring break normal shift.
Activity C5960 - C7110 - C5840 - C7090 will start in the spring break 2024.

- Please discuss this with your sub. due to clearances, containment, etc. This could take 5 days. update schedule accordingly.
Activity C6970 has its duration changed to 5 days.

- floors and ceilings need to be patched before school starts. please accelerate this scope to be complete by September 5.

The architectural work for the lower level/basement (Barr MS) has been pulled back to start by Mid-August and finish by the end of August.

- Refrigerant piping above ceilings may commence second shift during school year. We have spoken to the district. They are ok with temp ceiling removals during the school year.

Mechanical work for the first floor (Barr MS) will start in January 2024.

- Update for “Install New Roof Framing for Mechanical Equipment - Roof - Barr MS” during winter break 2023.

Mechanical work for the roof (Barr MS) was completed in January and will show their progress on update #02.