## Sheet1
Activity ID | Activity Name | Original Duration | Start | Finish | Actual Start | Actual Finish | Total Float | Physical % Complete
Nanuet Senior HS & Barr MS - Phase 3 - Update #04 |  | 352 | 26-Jun-23 A | 2024-10-29 | 2023-06-26 |  | 0
Milestones |  | 334 | 26-Jun-23 A | 2024-10-29 | 2023-06-26 |  | 0
M100 | NTP | 0 | 26-Jun-23 A |  | 2023-06-26 |  |  | 100%
M160 | Milestone 2 Nanuet Senior HS Start of Construction | 0 | 11-Jan-24 A |  | 2024-01-11 |  |  | 100%
M110 | Milestone 1 Building Envelope Substantial Completion | 0 |  | 15-Mar-24* |  |  | 179 | 0%
M150 | Milestone 1 Building Envelope Start of Construction | 0 | 18-Mar-24* |  |  |  | 0 | 0%
M170 | Milestone 3 Barr Senior HS HS Start of Construction | 0 | 26-Jun-24* |  |  |  | 0 | 0%
M130 | Milestone 2 Nanuet Senior HS Substantial Completion | 0 |  | 05-Sep-24* |  |  | 13 | 0%
M140 | Milestone 3 Barr Senior HS Substantial Completion | 0 |  | 19-Sep-24* |  |  | 0 | 0%
M120 | Final Completion | 0 |  | 29-Oct-24* |  |  | 0 | 0%
Pre-construction |  | 258 | 13-Sep-23 A | 2024-06-18 | 2023-09-13 |  | 65
Submittals |  | 247 | 13-Sep-23 A | 2024-06-18 | 2023-09-13 |  | 65
Division 5 - Metals |  | 75 | 31-Oct-23 A | 30-Nov-23 A | 2023-10-31 | 2023-11-30
Section 05 12 00 - Structural Steel |  | 75 | 31-Oct-23 A | 30-Nov-23 A | 2023-10-31 | 2023-11-30
S1040 | Prepare & Submit Structural Steel | 45 | 31-Oct-23 A | 03-Nov-23 A | 2023-10-31 | 2023-11-03 |  | 100%
S1050 | Review & Approve Structural Steel | 30 | 03-Nov-23 A | 30-Nov-23 A | 2023-11-03 | 2023-11-30 |  | 100%
Section 05 50 00 - Metal Fabrications |  | 75 | 31-Oct-23 A | 30-Nov-23 A | 2023-10-31 | 2023-11-30
S1060 | Prepare & Submit Metal Fabrications | 45 | 31-Oct-23 A | 03-Nov-23 A | 2023-10-31 | 2023-11-03 |  | 100%
S1070 | Review & Approve Metal Fabrications | 30 | 03-Nov-23 A | 30-Nov-23 A | 2023-11-03 | 2023-11-30 |  | 100%
Division 7 - Thermal And Moisture Protection |  | 199 | 11-Oct-23 A | 2024-04-11 | 2023-10-11 |  | 21
Section 07 71 00 Roof Curbs Rail And Portals |  | 75 | 11-Oct-23 A | 13-Oct-23 A | 2023-10-11 | 2023-10-13
S2610 | Prepare & Submit Roof Curbs Rail And Portals | 45 | 11-Oct-23 A | 13-Oct-23 A | 2023-10-11 | 2023-10-13 |  | 100%
S2620 | Review & Approve Roof Curbs Rail And Portals | 30 | 11-Oct-23 A | 13-Oct-23 A | 2023-10-11 | 2023-10-13 |  | 100%
Section 07 84 13 Penetration Firestopping |  | 91 | 11-Jan-24 A | 2024-04-11 | 2024-01-11 |  | 21
S2550 | Prepare & Submit Penetration Firestopping | 45 | 11-Jan-24 A | 11-Jan-24 A | 2024-01-11 | 2024-01-11 |  | 100%
S2560 | Review & Approve Penetration Firestopping | 30 | 11-Jan-24 A | 2024-04-11 | 2024-01-11 |  | 21 | 0%
Division 9 |  | 78 | 2024-03-01 | 2024-06-18 |  |  | 63
Section 09 51 23 Acoustical Ceiling Tile |  | 78 | 2024-03-01 | 2024-06-18 |  |  | 0
S2790 | Prepare & Submit Acoustical Ceiling Tile | 45 | 2024-03-01 | 2024-05-02 |  |  | 0 | 0%
S2800 | Review & Approve Acoustical Ceiling Tile | 33 | 2024-05-03 | 2024-06-18 |  |  | 0 | 0%
Section 09 65 13 Resilient Base And Accessories. |  | 75 | 2024-03-01 | 2024-06-13 |  |  | 66
S2830 | Prepare & Submit Resilient Base And Accessories. | 45 | 2024-03-01 | 2024-05-02 |  |  | 66 | 0%
S2840 | Review & Approve Resilient Base And Accessories. | 30 | 2024-05-03 | 2024-06-13 |  |  | 66 | 0%
Section 09 65 19 Resilient Flooring |  | 75 | 2024-03-01 | 2024-06-13 |  |  | 3
S2690 | Prepare & Submit Resilient Flooring | 45 | 2024-03-01 | 2024-05-02 |  |  | 3 | 0%
S2700 | Review & Approve Resilient Flooring | 30 | 2024-05-03 | 2024-06-13 |  |  | 3 | 0%
Division 23 - Heating, Ventilating, And Air-Conditioning (Hvac) |  | 212 | 13-Sep-23 A | 2024-04-26 | 2023-09-13 |  | 102
Section 23 05 16 Expansion Fittings And Loops For Hvac Piping |  | 75 | 14-Sep-23 A | 21-Sep-23 A | 2023-09-14 | 2023-09-21
S2010 | Prepare & Submit Expansion Fittings And Loops For Hvac Piping | 45 | 14-Sep-23 A | 21-Sep-23 A | 2023-09-14 | 2023-09-21 |  | 100%
S2020 | Review & Approve Expansion Fittings And Loops For Hvac Piping | 30 | 14-Sep-23 A | 21-Sep-23 A | 2023-09-14 | 2023-09-21 |  | 100%
Section 23 05 19 Meters And Gauges For Hvac Piping |  | 75 | 09-Oct-23 A | 28-Nov-23 A | 2023-10-09 | 2023-11-28
S1990 | Prepare & Submit Meters And Gauges For Hvac Piping | 45 | 09-Oct-23 A | 28-Nov-23 A | 2023-10-09 | 2023-11-28 |  | 100%
S2000 | Review & Approve Meters And Gauges For Hvac Piping | 30 | 09-Oct-23 A | 28-Nov-23 A | 2023-10-09 | 2023-11-28 |  | 100%
Section 23 05 48 Vibration Controls For Hvac Piping And Equipment |  | 75 | 10-Oct-23 A | 12-Oct-23 A | 2023-10-10 | 2023-10-12
S2110 | Prepare & Submit Vibration Controls For Hvac Piping And Equipment | 45 | 10-Oct-23 A | 12-Oct-23 A | 2023-10-10 | 2023-10-12 |  | 100%
S2120 | Review & Approve Vibration Controls For Hvac Piping And Equipment | 30 | 10-Oct-23 A | 12-Oct-23 A | 2023-10-10 | 2023-10-12 |  | 100%
Section 23 05 53 Identification For Hvac Piping And Equipment |  | 75 | 09-Oct-23 A | 09-Oct-23 A | 2023-10-09 | 2023-10-09
S2210 | Prepare & Submit Identification For Hvac Piping And Equipment | 45 | 09-Oct-23 A | 09-Oct-23 A | 2023-10-09 | 2023-10-09 |  | 100%
S2220 | Review & Approve Identification For Hvac Piping And Equipment | 30 | 09-Oct-23 A | 09-Oct-23 A | 2023-10-09 | 2023-10-09 |  | 100%
Section 23 05 93 Testing, Adjusting, And Balancing For Hvac |  | 75 | 09-Oct-23 A | 09-Oct-23 A | 2023-10-09 | 2023-10-09
S2310 | Prepare & Submit Testing, Adjusting, And Balancing For Hvac | 45 | 09-Oct-23 A | 09-Oct-23 A | 2023-10-09 | 2023-10-09 |  | 100%
S2320 | Review & Approve Testing, Adjusting, And Balancing For Hvac | 30 | 09-Oct-23 A | 09-Oct-23 A | 2023-10-09 | 2023-10-09 |  | 100%
Section 23 07 13 Duct Insulation |  | 75 | 20-Sep-23 A | 22-Sep-23 A | 2023-09-20 | 2023-09-22
S2410 | Prepare & Submit Duct Insulation | 45 | 20-Sep-23 A | 22-Sep-23 A | 2023-09-20 | 2023-09-22 |  | 100%
S2420 | Review & Approve Duct Insulation | 30 | 20-Sep-23 A | 22-Sep-23 A | 2023-09-20 | 2023-09-22 |  | 100%
Section 23 07 16 Hvac Equipment Insulation |  | 75 | 20-Sep-23 A | 22-Sep-23 A | 2023-09-20 | 2023-09-22
S2510 | Prepare & Submit HVAC Equipment Insulation | 45 | 20-Sep-23 A | 22-Sep-23 A | 2023-09-20 | 2023-09-22 |  | 100%
S2520 | Review & Approve HVAC Equipment Insulation | 30 | 20-Sep-23 A | 22-Sep-23 A | 2023-09-20 | 2023-09-22 |  | 100%
Section 23 07 19 Hvac Piping Insulation |  | 75 | 20-Sep-23 A | 22-Sep-23 A | 2023-09-20 | 2023-09-22
S1220 | Prepare & Submit HVAC Piping Insulation | 45 | 20-Sep-23 A | 22-Sep-23 A | 2023-09-20 | 2023-09-22 |  | 100%
S1230 | Review & Approve HVAC Piping Insulation | 30 | 20-Sep-23 A | 22-Sep-23 A | 2023-09-20 | 2023-09-22 |  | 100%
Section 23 08 00 Commissioning Of Hvac |  | 75 | 02-Nov-23 A | 09-Nov-23 A | 2023-11-02 | 2023-11-09
S1970 | Prepare & Submit Commissioning Of HVAC | 45 | 02-Nov-23 A | 09-Nov-23 A | 2023-11-02 | 2023-11-09 |  | 100%
S1980 | Review & Approve Commissioning Of HVAC | 30 | 02-Nov-23 A | 09-Nov-23 A | 2023-11-02 | 2023-11-09 |  | 100%
Section 23 09 23 Direct-Digital Control System For Hvac |  | 75 | 15-Dec-23 A | 2024-04-26 | 2023-12-15 |  | 93
S2090 | Prepare & Submit Direct-Digital Control System For Hvac | 45 | 15-Dec-23 A | 2024-04-26 | 2023-12-15 |  | 93 | 10%
S2100 | Review & Approve Direct-Digital Control System For Hvac | 30 | 15-Dec-23 A | 2024-04-08 | 2023-12-15 |  | 93 | 10%
Section 23 21 13 Hydronic Piping |  | 75 | 03-Nov-23 A | 08-Nov-23 A | 2023-11-03 | 2023-11-08
S2190 | Prepare & Submit Hydronic Piping | 45 | 03-Nov-23 A | 08-Nov-23 A | 2023-11-03 | 2023-11-08 |  | 100%
S2200 | Review & Approve Hydronic Piping | 30 | 03-Nov-23 A | 08-Nov-23 A | 2023-11-03 | 2023-11-08 |  | 100%
Section 23 21 14 Hydronic Specialties |  | 75 | 26-Oct-23 A | 26-Oct-23 A | 2023-10-26 | 2023-10-26
S2290 | Prepare & Submit Hydronic Specialties | 45 | 26-Oct-23 A | 26-Oct-23 A | 2023-10-26 | 2023-10-26 |  | 100%
S2300 | Review & Approve Hydronic Specialties | 30 | 26-Oct-23 A | 26-Oct-23 A | 2023-10-26 | 2023-10-26 |  | 100%
Section 23 21 23 Hydronic Pumps |  | 75 | 14-Sep-23 A | 21-Sep-23 A | 2023-09-14 | 2023-09-21
S2390 | Prepare & Submit Hydronic Pumps | 45 | 14-Sep-23 A | 21-Sep-23 A | 2023-09-14 | 2023-09-21 |  | 100%
S2400 | Review & Approve Hydronic Pumps | 30 | 14-Sep-23 A | 21-Sep-23 A | 2023-09-14 | 2023-09-21 |  | 100%
Section 23 22 13 Steam And Condensate Heating Piping |  | 75 | 14-Sep-23 A | 29-Sep-23 A | 2023-09-14 | 2023-09-29
S2490 | Prepare & Submit Steam And Condensate Heating Piping | 45 | 14-Sep-23 A | 29-Sep-23 A | 2023-09-14 | 2023-09-29 |  | 100%
S2500 | Review & Approve Steam And Condensate Heating Piping | 30 | 14-Sep-23 A | 29-Sep-23 A | 2023-09-14 | 2023-09-29 |  | 100%
Section 23 22 14 Steam And Condensate Heating Specialties |  | 75 | 20-Sep-23 A | 10-Oct-23 A | 2023-09-20 | 2023-10-10
S2050 | Prepare & Submit Steam And Condensate Heating Specialties | 45 | 20-Sep-23 A | 10-Oct-23 A | 2023-09-20 | 2023-10-10 |  | 100%
S2060 | Review & Approve Steam And Condensate Heating Specialties | 30 | 20-Sep-23 A | 10-Oct-23 A | 2023-09-20 | 2023-10-10 |  | 100%
Section 23 23 00 Refrigerant Piping |  | 75 | 25-Sep-23 A | 29-Sep-23 A | 2023-09-25 | 2023-09-29
S2150 | Prepare & Submit Refrigerant Piping | 45 | 25-Sep-23 A | 29-Sep-23 A | 2023-09-25 | 2023-09-29 |  | 100%
S2160 | Review & Approve Refrigerant Piping | 30 | 25-Sep-23 A | 29-Sep-23 A | 2023-09-25 | 2023-09-29 |  | 100%
Section 23 25 00 Hvac Water Treatment |  | 75 | 16-Jan-24 A | 2024-04-10 | 2024-01-16 |  | 114
S2250 | Prepare & Submit Hvac Water Treatment | 45 | 16-Jan-24 A | 08-Feb-24 A | 2024-01-16 | 2024-02-08 |  | 100%
S2260 | Review & Approve Hvac Water Treatment | 30 | 08-Feb-24 A | 2024-04-10 | 2024-02-08 |  | 114 | 5%
Section 23 31 00 Hvac Ducts And Casings |  | 75 | 12-Oct-23 A | 02-Nov-23 A | 2023-10-12 | 2023-11-02
S2350 | Prepare & Submit Hvac Ducts And Casings | 45 | 12-Oct-23 A | 02-Nov-23 A | 2023-10-12 | 2023-11-02 |  | 100%
S2360 | Review & Approve Hvac Ducts And Casings | 30 | 12-Oct-23 A | 02-Nov-23 A | 2023-10-12 | 2023-11-02 |  | 100%
Section 23 33 00 Air Duct Accessories |  | 75 | 25-Sep-23 A | 10-Oct-23 A | 2023-09-25 | 2023-10-10
S2450 | Prepare & Submit Air Duct Accessories | 45 | 25-Sep-23 A | 10-Oct-23 A | 2023-09-25 | 2023-10-10 |  | 100%
S2460 | Review & Approve Air Duct Accessories | 30 | 25-Sep-23 A | 10-Oct-23 A | 2023-09-25 | 2023-10-10 |  | 100%
Section 23 33 19 Duct Silencers |  | 75 | 28-Sep-23 A | 29-Sep-23 A | 2023-09-28 | 2023-09-29
S2070 | Prepare & Submit Duct Silencers | 45 | 28-Sep-23 A | 29-Sep-23 A | 2023-09-28 | 2023-09-29 |  | 100%
S2080 | Review & Approve Duct Silencers | 30 | 28-Sep-23 A | 29-Sep-23 A | 2023-09-28 | 2023-09-29 |  | 100%
Section 23 34 16 Centrifugal Hvac Fans |  | 75 | 29-Sep-23 A | 12-Oct-23 A | 2023-09-29 | 2023-10-12
S2170 | Prepare & Submit Centrifugal Hvac Fans | 45 | 29-Sep-23 A | 12-Oct-23 A | 2023-09-29 | 2023-10-12 |  | 100%
S2180 | Review & Approve Centrifugal Hvac Fans | 30 | 29-Sep-23 A | 12-Oct-23 A | 2023-09-29 | 2023-10-12 |  | 100%
Section 23 34 23 Hvac Power Ventilators |  | 75 | 29-Sep-23 A | 10-Oct-23 A | 2023-09-29 | 2023-10-10
S2270 | Prepare & Submit Hvac Power Ventilators | 45 | 29-Sep-23 A | 10-Oct-23 A | 2023-09-29 | 2023-10-10 |  | 100%
S2280 | Review & Approve Hvac Power Ventilators | 30 | 29-Sep-23 A | 10-Oct-23 A | 2023-09-29 | 2023-10-10 |  | 100%
Section 23 37 00 Air Outlets And Inlets |  | 75 | 25-Sep-23 A | 26-Sep-23 A | 2023-09-25 | 2023-09-26
S2370 | Prepare & Submit Air Outlets And Inlets | 45 | 25-Sep-23 A | 26-Sep-23 A | 2023-09-25 | 2023-09-26 |  | 100%
S2380 | Review & Approve Air Outlets And Inlets | 30 | 25-Sep-23 A | 26-Sep-23 A | 2023-09-25 | 2023-09-26 |  | 100%
Section 23 57 00 Heat Exchangers For Hvac |  | 75 | 15-Sep-23 A | 21-Sep-23 A | 2023-09-15 | 2023-09-21
S2470 | Prepare & Submit Heat Exchangers For Hvac | 45 | 15-Sep-23 A | 21-Sep-23 A | 2023-09-15 | 2023-09-21 |  | 100%
S2480 | Review & Approve Heat Exchangers For Hvac | 30 | 15-Sep-23 A | 21-Sep-23 A | 2023-09-15 | 2023-09-21 |  | 100%
Section 23 62 13 Air Cooled Refrigerant Compressor And Condenser Unit |  | 45 | 02-Nov-23 A | 27-Feb-24 A | 2023-11-02 | 2024-02-27
S2030 | Prepare & Submit Air Cooled Refrigerant Compressor And Condenser Unit | 45 | 02-Nov-23 A | 21-Nov-23 A | 2023-11-02 | 2023-11-21 |  | 100%
S2040 | Review & Approve Air Cooled Refrigerant Compressor And Condenser Unit | 30 | 22-Nov-23 A | 27-Feb-24 A | 2023-11-22 | 2024-02-27 |  | 100%
Section 23 73 13 Indoor Air-Handling Units |  | 75 | 13-Sep-23 A | 10-Oct-23 A | 2023-09-13 | 2023-10-10
S2130 | Prepare & Submit Indoor Air-Handling Units | 45 | 13-Sep-23 A | 10-Oct-23 A | 2023-09-13 | 2023-10-10 |  | 100%
S2140 | Review & Approve Indoor Air-Handling Units | 30 | 13-Sep-23 A | 10-Oct-23 A | 2023-09-13 | 2023-10-10 |  | 100%
Section 23 74 13 Packaged Rooftop Units |  | 75 | 02-Nov-23 A | 22-Nov-23 A | 2023-11-02 | 2023-11-22
S2230 | Prepare & Submit Packaged Rooftop Units | 45 | 02-Nov-23 A | 22-Nov-23 A | 2023-11-02 | 2023-11-22 |  | 100%
S2240 | Review & Approve Packaged Rooftop Units | 30 | 02-Nov-23 A | 22-Nov-23 A | 2023-11-02 | 2023-11-22 |  | 100%
Section 23 81 29 Variable Refrigerant Flow Hvac Systems |  | 75 | 02-Nov-23 A | 22-Nov-23 A | 2023-11-02 | 2023-11-22
S2330 | Prepare & Submit Variable Refrigerant Flow Hvac Systems | 45 | 02-Nov-23 A | 22-Nov-23 A | 2023-11-02 | 2023-11-22 |  | 100%
S2340 | Review & Approve Variable Refrigerant Flow Hvac Systems | 30 | 02-Nov-23 A | 22-Nov-23 A | 2023-11-02 | 2023-11-22 |  | 100%
Section 23 82 00 Convection Heating And Cooling Units |  | 75 | 13-Sep-23 A | 15-Sep-23 A | 2023-09-13 | 2023-09-15
S2430 | Prepare & Submit Convection Heating And Cooling Units | 45 | 13-Sep-23 A | 15-Sep-23 A | 2023-09-13 | 2023-09-15 |  | 100%
S2440 | Review & Approve Convection Heating And Cooling Units | 30 | 13-Sep-23 A | 15-Sep-23 A | 2023-09-13 | 2023-09-15 |  | 100%
Division 26 - Electrical |  | 75 | 15-Sep-23 A | 29-Sep-23 A | 2023-09-15 | 2023-09-29
Section 26 29 23 Variable-Frequency Motor Controllers |  | 75 | 15-Sep-23 A | 29-Sep-23 A | 2023-09-15 | 2023-09-29
S1670 | Prepare & Submit Variable-Frequency Motor Controllers | 45 | 15-Sep-23 A | 29-Sep-23 A | 2023-09-15 | 2023-09-29 |  | 100%
S1680 | Review & Approve Variable-Frequency Motor Controllers | 30 | 15-Sep-23 A | 29-Sep-23 A | 2023-09-15 | 2023-09-29 |  | 100%
Procurement |  | 183 | 13-Oct-23 A | 2024-04-18 | 2023-10-13 |  | 95
S1300 | Fabricate & Deliver Radaint Runtal Baseboard-MS-1 & 2 - SRS | 40 | 13-Oct-23 A | 15-Nov-23 A | 2023-10-13 | 2023-11-15 |  | 100%
S1310 | Fabricate & Deliver EF-8, 10, 21 & 23 Samtepp | 150 | 13-Oct-23 A | 06-Jan-24 A | 2023-10-13 | 2024-01-06 |  | 100%
S1320 | Fabricate & Deliver Dampers RKB | 88 | 13-Oct-23 A | 2024-04-17 | 2023-10-13 |  | 77 | 60%
S1340 | Fabricate & Deliver UV-MS- 1-41 D&B | 55 | 13-Oct-23 A | 15-Jan-24 A | 2023-10-13 | 2024-01-15 |  | 100%
S1350 | Fabricate & Deliver HP-MS-3-9 D&B | 60 | 13-Oct-23 A | 21-Nov-23 A | 2023-10-13 | 2023-11-21 |  | 100%
S1360 | Fabricate & Deliver CV-HS-1-11 | 40 | 13-Oct-23 A | 12-Nov-23 A | 2023-10-13 | 2023-11-12 |  | 100%
S1370 | Fabricate & Deliver UH-HS-1 GC Sales | 20 | 13-Oct-23 A | 08-Nov-23 A | 2023-10-13 | 2023-11-08 |  | 100%
S1380 | Fabricate & Deliver CUH- HS-1, 2, 3 GS Sales | 40 | 13-Oct-23 A | 30-Nov-23 A | 2023-10-13 | 2023-11-30 |  | 100%
S1390 | Fabricate & Deliver radinat runtal HS R2-1, 2, 3, & 4 SRS | 40 | 13-Oct-23 A | 15-Nov-23 A | 2023-10-13 | 2023-11-15 |  | 100%
S1400 | Fabricate & Deliver F-HS-2 & 3 D&B | 150 | 13-Oct-23 A | 2024-03-01 | 2023-10-13 | 2024-04-22 | 21 | 99%
S1410 | Fabricate & Deliver L-1 Louver with bird screen RKB | 88 | 13-Oct-23 A | 2024-04-18 | 2023-10-13 |  | 76 | 60%
S1420 | Fabricate & Deliver RTU-HS- 4 & 5 D&B | 110 | 13-Oct-23 A | 23-Feb-24 A | 2023-10-13 | 2024-02-23 |  | 100%
S1430 | Fabricate & Deliver BC-HS-1 & 2 D&B | 70 | 13-Oct-23 A | 21-Nov-23 A | 2023-10-13 | 2023-11-21 |  | 100%
S1440 | Fabricate & Deliver HC-HS-2 to 4 D&B | 40 | 13-Oct-23 A | 21-Nov-23 A | 2023-10-13 | 2023-11-21 |  | 100%
S1450 | Fabricate & Deliver AHU-HS-3 D&B | 120 | 13-Oct-23 A | 24-Jan-24 A | 2023-10-13 | 2024-01-24 |  | 100%
S1460 | Fabricate & Deliver ACCU-HS 2 D&B | 60 | 13-Oct-23 A | 01-Dec-23 A | 2023-10-13 | 2023-12-01 |  | 100%
S1470 | Fabricate & Deliver CP-HS-2 WE | 140 | 13-Oct-23 A | 05-Nov-23 A | 2023-10-13 | 2023-11-05 |  | 100%
S1480 | Fabricate & Deliver HX-HS-2 WE | 40 | 13-Oct-23 A | 02-Nov-23 A | 2023-10-13 | 2023-11-02 |  | 100%
S1490 | Fabricate & Deliver P-HS-3, 4, 5 & 6 WE | 120 | 13-Oct-23 A | 28-Nov-23 A | 2023-10-13 | 2023-11-28 |  | 100%
S1500 | Fabricate & Deliver B&G Suction Diffuser WE | 80 | 13-Oct-23 A | 05-Jan-24 A | 2023-10-13 | 2024-01-05 |  | 100%
S1510 | Fabricate & Deliver B&G Triple Duty Valve WE | 100 | 13-Oct-23 A | 06-Jan-24 A | 2023-10-13 | 2024-01-06 |  | 100%
S1520 | Fabricate & Deliver Flex Hose 6”X 24” WE | 30 | 13-Oct-23 A | 02-Nov-23 A | 2023-10-13 | 2023-11-02 |  | 100%
S1530 | Fabricate & Deliver EXP-HS-2 & 3 WE | 80 | 13-Oct-23 A | 20-Feb-24 A | 2023-10-13 | 2024-02-20 |  | 100%
S1540 | Fabricate & Deliver Flex Hose Exp Loops WE | 30 | 13-Oct-23 A | 02-Nov-23 A | 2023-10-13 | 2023-11-02 |  | 100%
S3200 | Fabricate & Deliver FT-MS-1 GC SALES | 35 | 13-Oct-23 A | 15-Nov-23 A | 2023-10-13 | 2023-11-15 |  | 100%
Construction |  | 246 | 10-Oct-23 A | 2024-09-19 | 2023-10-10 |  | 0
Mobilization |  | 10 | 10-Oct-23 A | 13-Oct-23 A | 2023-10-10 | 2023-10-13
C6920 | Mobilization & Site Prep. Mobilized demo of cielings | 10 | 10-Oct-23 A | 13-Oct-23 A | 2023-10-10 | 2023-10-13 |  | 100%
Nanuet Senior HS |  | 135 | 05-Jan-24 A | 2024-09-05 | 2024-01-05 |  | 9
Demolition |  | 14 | 2024-03-01 | 2024-03-20 |  |  | 66
C5920 | Remove Unit Ventilator - First Floor - Nanuet Senior HS | 1 | 2024-03-01 | 2024-03-01 |  |  | 64 | 0%
C7030 | Remove HVAC Ducts & Piping - Nanuet Senior HS | 14 | 2024-03-01 | 2024-03-20 |  |  | 66 | 50%
C5950 | Remove & Salvage Existing Wainscotting Pipe Enclosure - First Floor - Nanuet Senior HS | 1 | 2024-03-04 | 2024-03-04 |  |  | 64 | 0%
Basement |  | 127 | 05-Jan-24 A | 2024-06-27 | 2024-01-05 |  | 4
Architectural |  | 52 | 05-Jan-24 A | 2024-06-24 | 2024-01-05 |  | 4
C6870 | Patch Ceilings - Basement - Nanuet Senior HS | 2 | 05-Jan-24 A | 2024-06-18 | 2024-01-05 |  | 0 | 25%
C6910 | Patch Walls - Basement - Nanuet Senior HS | 3 | 2024-06-19 | 2024-06-21 |  |  | 0 | 25%
C6760 | Patch Flooring - Basement - Nanuet Senior HS | 1 | 2024-06-24 | 2024-06-24 |  |  | 4 | 25%
Mechanical |  | 125 | 11-Jan-24 A | 2024-06-27 | 2024-01-11 |  | 4
C6600 | Install Mechanical Ducts & Pipes Hangers - Basement - Nanuet Senior HS | 2 | 11-Jan-24 A | 2024-03-04 | 2024-01-11 |  | 64 | 100%
C6610 | Install HVAC Ducts & Pipes - Basement - Nanuet Senior HS | 10 | 11-Jan-24 A | 2024-03-20 | 2024-01-11 |  | 66 | 75%
C6630 | Install Above ceiling Terminal Equipment - Basement - Nanuet Senior HS | 6 | 11-Jan-24 A | 2024-03-08 | 2024-01-11 |  | 80 | 100%
C7120 | Install Mechanical Equipment - Basement - Nanuet Senior HS | 10 | 11-Jan-24 A | 2024-06-27 | 2024-01-11 |  | 4 | 100%
C6640 | Mechanical Rough-Ins Inspection - Basement - Nanuet Senior HS | 3 | 25-Jan-24 A | 2024-03-05 | 2024-01-25 |  | 81 | 100%
C6650 | Mechanical Rough-Ins Punchlist - Basement - Nanuet Senior HS | 3 | 2024-03-05 | 2024-03-08 |  |  | 81 | 0%
C6620 | Insulate HVAC Ducts & Pipes - Basement - Nanuet Senior HS | 1 | 2024-06-25 | 2024-06-25 |  |  | 4 | 65%
C6660 | Install Grilles & Difussers - Basement - Nanuet Senior HS | 2 | 2024-06-26 | 2024-06-27 |  |  | 4 | 0%
First Floor |  | 110 | 05-Jan-24 A | 2024-07-17 | 2024-01-05 |  | 0
Architectural |  | 33 | 05-Jan-24 A | 2024-07-02 | 2024-01-05 |  | 0
C6550 | Patch Ceilings - First Floor - Nanuet Senior HS | 2 | 05-Jan-24 A | 2024-06-18 | 2024-01-05 |  | 3 | 20%
C6590 | Patch Walls - First Floor - Nanuet Senior HS | 2 | 2024-06-24 | 2024-06-25 |  |  | 0 | 20%
C6440 | Patch Flooring - First Floor - Nanuet Senior HS | 5 | 2024-06-26 | 2024-07-02 |  |  | 0 | 0%
Mechanical |  | 98 | 11-Jan-24 A | 2024-07-17 | 2024-01-11 |  | 0
C6280 | Install Mechanical Ducts & Pipes Hangers - First Floor - Nanuet Senior HS | 2 | 11-Jan-24 A | 2024-03-06 | 2024-01-11 |  | 64 | 65%
C6290 | Install HVAC Ducts & Pipes - First Floor - Nanuet Senior HS | 10 | 11-Jan-24 A | 2024-03-15 | 2024-01-11 |  | 64 | 65%
C6310 | Install Above ceiling Terminal Equipment - First Floor - Nanuet Senior HS | 6 | 2024-03-06 | 2024-03-14 |  |  | 66 | 95%
C6300 | Insulate HVAC Ducts & Pipes - First Floor - Nanuet Senior HS | 1 | 2024-03-15 | 2024-03-18 |  |  | 64 | 65%
C6320 | Mechanical Rough-Ins Inspection - First Floor - Nanuet Senior HS | 2 | 2024-03-18 | 2024-03-20 |  |  | 64 | 65%
C6330 | Mechanical Rough-Ins Punchlist - First Floor - Nanuet Senior HS | 3 | 2024-03-20 | 2024-03-25 |  |  | 64 | 0%
C6340 | Install Grilles & Difussers - First Floor - Nanuet Senior HS | 1 | 2024-03-25 | 2024-03-26 |  |  | 70 | 0%
C7100 | Install Mechanical Equipment - First Floor - Nanuet Senior HS | 10 | 2024-07-03 | 2024-07-17 |  |  | 0 | 95%
Second Floor |  | 88 | 05-Jan-24 A | 2024-07-16 | 2024-01-05 |  | 46
Architectural |  | 29 | 05-Jan-24 A | 2024-06-25 | 2024-01-05 |  | 59
C6230 | Patch Ceilings - Second Floor - Nanuet Senior HS | 2 | 05-Jan-24 A | 2024-06-19 | 2024-01-05 |  | 36 | 65%
C6270 | Patch Walls - Second Floor - Nanuet Senior HS | 3 | 2024-06-19 | 2024-06-24 |  |  | 59 | 65%
C6120 | Patch Flooring - Second Floor - Nanuet Senior HS | 1 | 2024-06-24 | 2024-06-25 |  |  | 59 | 65%
Mechanical |  | 76 | 11-Jan-24 A | 2024-07-16 | 2024-01-11 |  | 46
C5960 | Install Mechanical Ducts & Pipes Hangers - Second Floor - Nanuet Senior HS | 1 | 11-Jan-24 A | 2024-04-01 | 2024-01-11 |  | 4 | 95%
C7110 | Install Mechanical Equipment - Second Floor - Nanuet Senior HS | 4 | 11-Jan-24 A | 2024-04-01 | 2024-01-11 |  | 4 | 95%
C5970 | Install HVAC Ducts & Pipes - Second Floor - Nanuet Senior HS | 10 | 2024-06-19 | 2024-07-03 |  |  | 36 | 65%
C5990 | Install Above ceiling Terminal Equipment - Second Floor - Nanuet Senior HS | 6 | 2024-06-19 | 2024-06-27 |  |  | 40 | 95%
C5980 | Insulate HVAC Ducts & Pipes - Second Floor - Nanuet Senior HS | 1 | 2024-07-03 | 2024-07-05 |  |  | 36 | 65%
C6000 | Mechanical Rough-Ins Inspection - Second Floor - Nanuet Senior HS | 3 | 2024-07-05 | 2024-07-10 |  |  | 36 | 65%
C6010 | Mechanical Rough-Ins Punchlist - Second Floor - Nanuet Senior HS | 3 | 2024-07-10 | 2024-07-15 |  |  | 36 | 0%
C6020 | Install Grilles & Difussers - Second Floor - Nanuet Senior HS | 1 | 2024-07-15 | 2024-07-16 |  |  | 45 | 0%
Roof |  | 85 | 15-Jan-24 A | 2024-04-05 | 2024-01-15 |  | 107
Structural |  | 5 | 15-Jan-24 A | 2024-03-11 | 2024-01-15 |  | 14
C5840 | Install New Roof Steel Framing for Mechanical Equipment - Roof - Nanuet Senior HS | 5 | 15-Jan-24 A | 2024-03-11 | 2024-01-15 |  | 14 | 100%
Mechanical |  | 85 | 15-Jan-24 A | 2024-04-05 | 2024-01-15 |  | 107
C5880 | Install New Mechanical Equipment Curbs Equipment Rails & Pitch Pockets - Roof - Nanuet Senior HS | 4 | 15-Jan-24 A | 2024-03-15 | 2024-01-15 |  | 21 | 100%
C7130 | Install ACCU-HS-2 - Roof - Nanuet Senior HS | 12 | 15-Jan-24 A | 2024-03-15 | 2024-01-15 |  | 120 | 100%
C5870 | Remove Roof Top Exhaust Fan & All Associated Controls & Wiring - Roof - Nanuet Senior HS | 5 | 2024-04-01 | 2024-04-05 |  |  | 0 | 100%
C7090 | Install RTUs 4,5 - Roof - Nanuet Senior HS (Crane Pick) | 3 | 2024-04-01 | 2024-04-03 |  |  | 0 | 100%
C7190 | Install RTUs 4,5 - Roof - Nanuet Senior HS (RTU Connections) | 5 | 2024-04-01 | 2024-04-05 |  |  | 0 | 100%
Testing & Commissioning |  | 46 | 2024-07-04 | 2024-09-05 |  |  | 9
A1000 | Install Mechanical Controls - Nanuet Senior HS | 34 | 2024-07-04 | 2024-08-20 |  |  | 0 | 10%
A1010 | Point-To-Point checks - Nanuet Senior HS | 15 | 2024-08-01 | 2024-08-21 |  |  | 10 | 0%
TC100 | HVAC Testing & Balancing - Nanuet Senior HS | 5 | 2024-08-21 | 2024-08-28 |  |  | 9 | 0%
TC110 | HVAC Commissioning - Nanuet Senior HS | 5 | 2024-08-28 | 2024-09-05 |  |  | 9 | 0%
Barr MS |  | 210 | 05-Jan-24 A | 2024-09-19 | 2024-01-05 |  | 0
Demolition |  | 14 | 2024-07-05 | 2024-07-24 |  |  | 20
C6950 | Remove Unit Ventilators - Barr MS | 2 | 2024-07-05 | 2024-07-08 |  |  | 12 | 0%
C6960 | Remove Casework - Barr MS | 1 | 2024-07-09 | 2024-07-09 |  |  | 12 | 0%
C6970 | Remove Portion of Existing VAT Flooring - Barr MS Asbestos Subcontractor | 6 | 2024-07-10 | 2024-07-17 |  |  | 12 | 0%
C7020 | Remove HVAC Ducts & Pipes & Piping - Barr MS | 11 | 2024-07-10 | 2024-07-24 |  |  | 20 | 0%
Asbestos Abatement Barr MS |  | 3 | 2024-07-15 | 2024-07-17 |  |  | 12
C1010 | Perform Asbestos Abatement @ First Floor - Barr MS | 3 | 2024-07-15 | 2024-07-17 |  |  | 12 | 0%
C1020 | Perform Asbestos Abatement @ Second Floor - Barr MS | 3 | 2024-07-15 | 2024-07-17 |  |  | 12 | 0%
Lower Level/Basement |  | 5 | 2024-07-18 | 2024-07-24 |  |  | 23
Architectural |  | 5 | 2024-07-18 | 2024-07-24 |  |  | 23
C5170 | Patch Floor - Lower Level - Barr MS | 5 | 2024-07-18 | 2024-07-24 |  |  | 23 | 0%
C5280 | Patch Ceilings - Lower Level - Barr MS | 5 | 2024-07-18 | 2024-07-24 |  |  | 23 | 0%
C5320 | Patch Walls - Lower Level - Barr MS | 5 | 2024-07-18 | 2024-07-24 |  |  | 23 | 0%
First Floor |  | 106 | 08-Jan-24 A | 2024-08-19 | 2024-01-08 |  | 22
Architectural |  | 106 | 08-Jan-24 A | 2024-08-19 | 2024-01-08 |  | 22
C4070 | Patch Ceilings - First Floor - Barr MS | 2 | 08-Jan-24 A | 2024-07-24 | 2024-01-08 |  | 26 | 45%
C4080 | Install Casework - First Floor - Barr MS | 1 | 2024-07-25 | 2024-07-25 |  |  | 39 | 0%
C4140 | Patch Walls - First Floor - Barr MS | 3 | 2024-08-09 | 2024-08-13 |  |  | 12 | 0%
C3720 | Patch Flooring - First Floor - Barr MS | 4 | 2024-08-14 | 2024-08-19 |  |  | 12 | 0%
Mechanical |  | 16 | 2024-07-18 | 2024-08-08 |  |  | 12
C3730 | Install Mechanical Ducts & Pipes Hangers - First Floor - Barr MS | 1 | 2024-07-18 | 2024-07-18 |  |  | 12 | 95%
C3750 | Install HVAC Ducts & Pipes - First Floor - Barr MS | 12 | 2024-07-18 | 2024-08-02 |  |  | 12 | 90%
C3760 | Install Above ceiling Terminal Equipment & Unit Ventilator 15 - First Floor - Barr MS | 4 | 2024-07-19 | 2024-07-24 |  |  | 15 | 0%
C3800 | Insulate HVAC Ducts & Pipes - First Floor - Barr MS | 1 | 2024-07-24 | 2024-07-24 |  |  | 15 | 90%
C3870 | Mechanical Rough-Ins Inspection - First Floor - Barr MS | 2 | 2024-07-25 | 2024-07-26 |  |  | 15 | 50%
C3880 | Mechanical Rough-Ins Punchlist - First Floor - Barr MS | 2 | 2024-07-29 | 2024-07-30 |  |  | 15 | 0%
C4090 | Install Grilles & Difussers - First Floor - Barr MS | 4 | 2024-08-05 | 2024-08-08 |  |  | 12 | 0%
Second Floor |  | 34 | 05-Jan-24 A | 2024-09-03 | 2024-01-05 |  | 12
Architectural |  | 28 | 05-Jan-24 A | 2024-09-03 | 2024-01-05 |  | 12
C4780 | Patch Ceiling - Second Floor - Barr MS | 6 | 05-Jan-24 A | 2024-08-19 | 2024-01-05 |  | 12 | 50%
C4890 | Patch Walls - Second Floor - Barr MS | 4 | 08-Jan-24 A | 2024-08-19 | 2024-01-08 |  | 12 | 45%
C4900 | Install Casework - Second Floor - Barr MS | 1 | 2024-07-26 | 2024-07-26 |  |  | 39 | 0%
C4830 | Patch Flooring - Second Floor - Barr MS | 10 | 2024-08-20 | 2024-09-03 |  |  | 12 | 0%
Mechanical |  | 13 | 2024-07-18 | 2024-08-05 |  |  | 12
C4540 | Install Mechanical Ducts & Pipes Hangers - Second Floor - Barr MS | 1 | 2024-07-18 | 2024-07-18 |  |  | 12 | 90%
C4550 | Install HVAC Ducts & Pipes - Second Floor - Barr MS | 8 | 2024-07-18 | 2024-07-29 |  |  | 16 | 65%
C4570 | Install Above ceiling Terminal Equipment & unit Ventilator 24 - Second Floor - Barr MS | 4 | 2024-07-19 | 2024-07-24 |  |  | 12 | 0%
C4560 | Insulate HVAC Ducts & Pipes - Second Floor - Barr MS | 1 | 2024-07-24 | 2024-07-24 |  |  | 12 | 90%
C4580 | Mechanical Rough-Ins Inspection - Second Floor - Barr MS | 2 | 2024-07-25 | 2024-07-26 |  |  | 12 | 50%
C4590 | Mechanical Rough-Ins Punchlist - Second Floor - Barr MS | 3 | 2024-07-29 | 2024-07-31 |  |  | 12 | 0%
C4600 | Install Grilles & Difussers - Second Floor - Barr MS | 3 | 2024-08-01 | 2024-08-05 |  |  | 12 | 0%
Roof |  | 41 | 05-Jan-24 A | 2024-04-02 | 2024-01-05 |  | 100
Structural |  | 4 | 05-Jan-24 A | 2024-04-02 | 2024-01-05 |  | 14
C1030 | Install New Roof Framing for Mechanical Equipment - Roof - Barr MS | 4 | 05-Jan-24 A | 2024-04-02 | 2024-01-05 |  | 14 | 100%
Mechanical |  | 41 | 05-Jan-24 A | 23-Jan-24 A | 2024-01-05 | 2024-01-23
C5770 | Remove Roof Top Exhaust Fan & All Associated Controls & Wiring - Roof - Barr MS | 14 | 05-Jan-24 A | 16-Jan-24 A | 2024-01-05 | 2024-01-16 |  | 100%
S2980 | Install HP-MS-3-9 - Roof - Barr MS | 17 | 05-Jan-24 A | 16-Jan-24 A | 2024-01-05 | 2024-01-16 |  | 100%
C7140 | Install New Mechanical Equipment - Roof - Barr MS | 17 | 05-Jan-24 A | 23-Jan-24 A | 2024-01-05 | 2024-01-23 |  | 100%
S2940 | Install EF-8, 10, 21 & 23 - Roof - Barr MS | 17 | 11-Jan-24 A | 16-Jan-24 A | 2024-01-11 | 2024-01-16 |  | 100%
Testing & Commissioning - Barr MS |  | 56 | 2024-07-04 | 2024-09-19 |  |  | 0
A1020 | Install Mechanical Controls - Barr MS | 40 | 2024-07-04 | 2024-08-28 |  |  | 0 | 10%
A1030 | Point-To-Point checks - Barr MS | 15 | 2024-08-01 | 2024-08-21 |  |  | 0 | 0%
TC120 | HVAC Testing & Balancing - Barr MS | 10 | 2024-08-21 | 2024-09-05 |  |  | 0 | 0%
TC130 | HVAC Commissioning - Barr MS | 10 | 2024-09-05 | 2024-09-19 |  |  | 0 | 0%
Close Outs |  | 27 | 2024-09-19 | 2024-10-29 |  |  | 0
CLO100 | Final Inspections | 6 | 2024-09-19 | 2024-09-27 |  |  | 0 | 0%
CLO110 | Punchlist | 10 | 2024-09-27 | 2024-10-11 |  |  | 0 | 0%
CLO120 | Final Clean Up | 6 | 2024-10-11 | 2024-10-22 |  |  | 0 | 0%
CLO130 | Demobilization | 5 | 2024-10-22 | 2024-10-29 |  |  | 0 | 0%

## Sheet1 (2) (hidden)
Activity ID | Activity Name | Original Duration | Start | Finish | Actual Start | Actual Finish | Total Float | Physical % Complete
Nanuet Senior HS & Barr MS - Phase 3 - Update #04 |  | 352 | 26-Jun-23 A | 2024-10-29 | 2023-06-26 |  | 0
Milestones |  | 334 | 26-Jun-23 A | 2024-10-29 | 2023-06-26 |  | 0
M100 | NTP | 0 | 26-Jun-23 A |  | 2023-06-26 |  |  | 100%
M160 | Milestone 2 Nanuet Senior HS Start of Construction | 0 | 11-Jan-24 A |  | 2024-01-11 |  |  | 100%
M110 | Milestone 1 Building Envelope Substantial Completion | 0 |  | 15-Mar-24* |  |  | 179 | 0%
M150 | Milestone 1 Building Envelope Start of Construction | 0 | 18-Mar-24* |  |  |  | 0 | 0%
M170 | Milestone 3 Barr Senior HS HS Start of Construction | 0 | 26-Jun-24* |  |  |  | 0 | 0%
M130 | Milestone 2 Nanuet Senior HS Substantial Completion | 0 |  | 05-Sep-24* |  |  | 13 | 0%
M140 | Milestone 3 Barr Senior HS Substantial Completion | 0 |  | 19-Sep-24* |  |  | 0 | 0%
M120 | Final Completion | 0 |  | 29-Oct-24* |  |  | 0 | 0%
Pre-construction |  | 258 | 13-Sep-23 A | 2024-06-18 | 2023-09-13 |  | 65
Submittals |  | 247 | 13-Sep-23 A | 2024-06-18 | 2023-09-13 |  | 65
Division 5 - Metals |  | 75 | 31-Oct-23 A | 30-Nov-23 A | 2023-10-31 | 2023-11-30
Section 05 12 00 - Structural Steel |  | 75 | 31-Oct-23 A | 30-Nov-23 A | 2023-10-31 | 2023-11-30
S1040 | Prepare & Submit Structural Steel | 45 | 31-Oct-23 A | 03-Nov-23 A | 2023-10-31 | 2023-11-03 |  | 100%
S1050 | Review & Approve Structural Steel | 30 | 03-Nov-23 A | 30-Nov-23 A | 2023-11-03 | 2023-11-30 |  | 100%
Section 05 50 00 - Metal Fabrications |  | 75 | 31-Oct-23 A | 30-Nov-23 A | 2023-10-31 | 2023-11-30
S1060 | Prepare & Submit Metal Fabrications | 45 | 31-Oct-23 A | 03-Nov-23 A | 2023-10-31 | 2023-11-03 |  | 100%
S1070 | Review & Approve Metal Fabrications | 30 | 03-Nov-23 A | 30-Nov-23 A | 2023-11-03 | 2023-11-30 |  | 100%
Division 7 - Thermal And Moisture Protection |  | 199 | 11-Oct-23 A | 2024-04-11 | 2023-10-11 |  | 21
Section 07 71 00 Roof Curbs Rail And Portals |  | 75 | 11-Oct-23 A | 13-Oct-23 A | 2023-10-11 | 2023-10-13
S2610 | Prepare & Submit Roof Curbs Rail And Portals | 45 | 11-Oct-23 A | 13-Oct-23 A | 2023-10-11 | 2023-10-13 |  | 100%
S2620 | Review & Approve Roof Curbs Rail And Portals | 30 | 11-Oct-23 A | 13-Oct-23 A | 2023-10-11 | 2023-10-13 |  | 100%
Section 07 84 13 Penetration Firestopping |  | 91 | 11-Jan-24 A | 2024-04-11 | 2024-01-11 |  | 21
S2550 | Prepare & Submit Penetration Firestopping | 45 | 11-Jan-24 A | 11-Jan-24 A | 2024-01-11 | 2024-01-11 |  | 100%
S2560 | Review & Approve Penetration Firestopping | 30 | 11-Jan-24 A | 2024-04-11 | 2024-01-11 |  | 21 | 0%
Division 9 |  | 78 | 2024-03-01 | 2024-06-18 |  |  | 63
Section 09 51 23 Acoustical Ceiling Tile |  | 78 | 2024-03-01 | 2024-06-18 |  |  | 0
S2790 | Prepare & Submit Acoustical Ceiling Tile | 45 | 2024-03-01 | 2024-05-02 |  |  | 0 | 0%
S2800 | Review & Approve Acoustical Ceiling Tile | 33 | 2024-05-03 | 2024-06-18 |  |  | 0 | 0%
Section 09 65 13 Resilient Base And Accessories. |  | 75 | 2024-03-01 | 2024-06-13 |  |  | 66
S2830 | Prepare & Submit Resilient Base And Accessories. | 45 | 2024-03-01 | 2024-05-02 |  |  | 66 | 0%
S2840 | Review & Approve Resilient Base And Accessories. | 30 | 2024-05-03 | 2024-06-13 |  |  | 66 | 0%
Section 09 65 19 Resilient Flooring |  | 75 | 2024-03-01 | 2024-06-13 |  |  | 3
S2690 | Prepare & Submit Resilient Flooring | 45 | 2024-03-01 | 2024-05-02 |  |  | 3 | 0%
S2700 | Review & Approve Resilient Flooring | 30 | 2024-05-03 | 2024-06-13 |  |  | 3 | 0%
Division 23 - Heating, Ventilating, And Air-Conditioning (Hvac) |  | 212 | 13-Sep-23 A | 2024-04-26 | 2023-09-13 |  | 102
Section 23 05 16 Expansion Fittings And Loops For Hvac Piping |  | 75 | 14-Sep-23 A | 21-Sep-23 A | 2023-09-14 | 2023-09-21
S2010 | Prepare & Submit Expansion Fittings And Loops For Hvac Piping | 45 | 14-Sep-23 A | 21-Sep-23 A | 2023-09-14 | 2023-09-21 |  | 100%
S2020 | Review & Approve Expansion Fittings And Loops For Hvac Piping | 30 | 14-Sep-23 A | 21-Sep-23 A | 2023-09-14 | 2023-09-21 |  | 100%
Section 23 05 19 Meters And Gauges For Hvac Piping |  | 75 | 09-Oct-23 A | 28-Nov-23 A | 2023-10-09 | 2023-11-28
S1990 | Prepare & Submit Meters And Gauges For Hvac Piping | 45 | 09-Oct-23 A | 28-Nov-23 A | 2023-10-09 | 2023-11-28 |  | 100%
S2000 | Review & Approve Meters And Gauges For Hvac Piping | 30 | 09-Oct-23 A | 28-Nov-23 A | 2023-10-09 | 2023-11-28 |  | 100%
Section 23 05 48 Vibration Controls For Hvac Piping And Equipment |  | 75 | 10-Oct-23 A | 12-Oct-23 A | 2023-10-10 | 2023-10-12
S2110 | Prepare & Submit Vibration Controls For Hvac Piping And Equipment | 45 | 10-Oct-23 A | 12-Oct-23 A | 2023-10-10 | 2023-10-12 |  | 100%
S2120 | Review & Approve Vibration Controls For Hvac Piping And Equipment | 30 | 10-Oct-23 A | 12-Oct-23 A | 2023-10-10 | 2023-10-12 |  | 100%
Section 23 05 53 Identification For Hvac Piping And Equipment |  | 75 | 09-Oct-23 A | 09-Oct-23 A | 2023-10-09 | 2023-10-09
S2210 | Prepare & Submit Identification For Hvac Piping And Equipment | 45 | 09-Oct-23 A | 09-Oct-23 A | 2023-10-09 | 2023-10-09 |  | 100%
S2220 | Review & Approve Identification For Hvac Piping And Equipment | 30 | 09-Oct-23 A | 09-Oct-23 A | 2023-10-09 | 2023-10-09 |  | 100%
Section 23 05 93 Testing, Adjusting, And Balancing For Hvac |  | 75 | 09-Oct-23 A | 09-Oct-23 A | 2023-10-09 | 2023-10-09
S2310 | Prepare & Submit Testing, Adjusting, And Balancing For Hvac | 45 | 09-Oct-23 A | 09-Oct-23 A | 2023-10-09 | 2023-10-09 |  | 100%
S2320 | Review & Approve Testing, Adjusting, And Balancing For Hvac | 30 | 09-Oct-23 A | 09-Oct-23 A | 2023-10-09 | 2023-10-09 |  | 100%
Section 23 07 13 Duct Insulation |  | 75 | 20-Sep-23 A | 22-Sep-23 A | 2023-09-20 | 2023-09-22
S2410 | Prepare & Submit Duct Insulation | 45 | 20-Sep-23 A | 22-Sep-23 A | 2023-09-20 | 2023-09-22 |  | 100%
S2420 | Review & Approve Duct Insulation | 30 | 20-Sep-23 A | 22-Sep-23 A | 2023-09-20 | 2023-09-22 |  | 100%
Section 23 07 16 Hvac Equipment Insulation |  | 75 | 20-Sep-23 A | 22-Sep-23 A | 2023-09-20 | 2023-09-22
S2510 | Prepare & Submit HVAC Equipment Insulation | 45 | 20-Sep-23 A | 22-Sep-23 A | 2023-09-20 | 2023-09-22 |  | 100%
S2520 | Review & Approve HVAC Equipment Insulation | 30 | 20-Sep-23 A | 22-Sep-23 A | 2023-09-20 | 2023-09-22 |  | 100%
Section 23 07 19 Hvac Piping Insulation |  | 75 | 20-Sep-23 A | 22-Sep-23 A | 2023-09-20 | 2023-09-22
S1220 | Prepare & Submit HVAC Piping Insulation | 45 | 20-Sep-23 A | 22-Sep-23 A | 2023-09-20 | 2023-09-22 |  | 100%
S1230 | Review & Approve HVAC Piping Insulation | 30 | 20-Sep-23 A | 22-Sep-23 A | 2023-09-20 | 2023-09-22 |  | 100%
Section 23 08 00 Commissioning Of Hvac |  | 75 | 02-Nov-23 A | 09-Nov-23 A | 2023-11-02 | 2023-11-09
S1970 | Prepare & Submit Commissioning Of HVAC | 45 | 02-Nov-23 A | 09-Nov-23 A | 2023-11-02 | 2023-11-09 |  | 100%
S1980 | Review & Approve Commissioning Of HVAC | 30 | 02-Nov-23 A | 09-Nov-23 A | 2023-11-02 | 2023-11-09 |  | 100%
Section 23 09 23 Direct-Digital Control System For Hvac |  | 75 | 15-Dec-23 A | 2024-04-26 | 2023-12-15 |  | 93
S2090 | Prepare & Submit Direct-Digital Control System For Hvac | 45 | 15-Dec-23 A | 2024-04-26 | 2023-12-15 |  | 93 | 10%
S2100 | Review & Approve Direct-Digital Control System For Hvac | 30 | 15-Dec-23 A | 2024-04-08 | 2023-12-15 |  | 93 | 10%
Section 23 21 13 Hydronic Piping |  | 75 | 03-Nov-23 A | 08-Nov-23 A | 2023-11-03 | 2023-11-08
S2190 | Prepare & Submit Hydronic Piping | 45 | 03-Nov-23 A | 08-Nov-23 A | 2023-11-03 | 2023-11-08 |  | 100%
S2200 | Review & Approve Hydronic Piping | 30 | 03-Nov-23 A | 08-Nov-23 A | 2023-11-03 | 2023-11-08 |  | 100%
Section 23 21 14 Hydronic Specialties |  | 75 | 26-Oct-23 A | 26-Oct-23 A | 2023-10-26 | 2023-10-26
S2290 | Prepare & Submit Hydronic Specialties | 45 | 26-Oct-23 A | 26-Oct-23 A | 2023-10-26 | 2023-10-26 |  | 100%
S2300 | Review & Approve Hydronic Specialties | 30 | 26-Oct-23 A | 26-Oct-23 A | 2023-10-26 | 2023-10-26 |  | 100%
Section 23 21 23 Hydronic Pumps |  | 75 | 14-Sep-23 A | 21-Sep-23 A | 2023-09-14 | 2023-09-21
S2390 | Prepare & Submit Hydronic Pumps | 45 | 14-Sep-23 A | 21-Sep-23 A | 2023-09-14 | 2023-09-21 |  | 100%
S2400 | Review & Approve Hydronic Pumps | 30 | 14-Sep-23 A | 21-Sep-23 A | 2023-09-14 | 2023-09-21 |  | 100%
Section 23 22 13 Steam And Condensate Heating Piping |  | 75 | 14-Sep-23 A | 29-Sep-23 A | 2023-09-14 | 2023-09-29
S2490 | Prepare & Submit Steam And Condensate Heating Piping | 45 | 14-Sep-23 A | 29-Sep-23 A | 2023-09-14 | 2023-09-29 |  | 100%
S2500 | Review & Approve Steam And Condensate Heating Piping | 30 | 14-Sep-23 A | 29-Sep-23 A | 2023-09-14 | 2023-09-29 |  | 100%
Section 23 22 14 Steam And Condensate Heating Specialties |  | 75 | 20-Sep-23 A | 10-Oct-23 A | 2023-09-20 | 2023-10-10
S2050 | Prepare & Submit Steam And Condensate Heating Specialties | 45 | 20-Sep-23 A | 10-Oct-23 A | 2023-09-20 | 2023-10-10 |  | 100%
S2060 | Review & Approve Steam And Condensate Heating Specialties | 30 | 20-Sep-23 A | 10-Oct-23 A | 2023-09-20 | 2023-10-10 |  | 100%
Section 23 23 00 Refrigerant Piping |  | 75 | 25-Sep-23 A | 29-Sep-23 A | 2023-09-25 | 2023-09-29
S2150 | Prepare & Submit Refrigerant Piping | 45 | 25-Sep-23 A | 29-Sep-23 A | 2023-09-25 | 2023-09-29 |  | 100%
S2160 | Review & Approve Refrigerant Piping | 30 | 25-Sep-23 A | 29-Sep-23 A | 2023-09-25 | 2023-09-29 |  | 100%
Section 23 25 00 Hvac Water Treatment |  | 75 | 16-Jan-24 A | 2024-04-10 | 2024-01-16 |  | 114
S2250 | Prepare & Submit Hvac Water Treatment | 45 | 16-Jan-24 A | 08-Feb-24 A | 2024-01-16 | 2024-02-08 |  | 100%
S2260 | Review & Approve Hvac Water Treatment | 30 | 08-Feb-24 A | 2024-04-10 | 2024-02-08 |  | 114 | 5%
Section 23 31 00 Hvac Ducts And Casings |  | 75 | 12-Oct-23 A | 02-Nov-23 A | 2023-10-12 | 2023-11-02
S2350 | Prepare & Submit Hvac Ducts And Casings | 45 | 12-Oct-23 A | 02-Nov-23 A | 2023-10-12 | 2023-11-02 |  | 100%
S2360 | Review & Approve Hvac Ducts And Casings | 30 | 12-Oct-23 A | 02-Nov-23 A | 2023-10-12 | 2023-11-02 |  | 100%
Section 23 33 00 Air Duct Accessories |  | 75 | 25-Sep-23 A | 10-Oct-23 A | 2023-09-25 | 2023-10-10
S2450 | Prepare & Submit Air Duct Accessories | 45 | 25-Sep-23 A | 10-Oct-23 A | 2023-09-25 | 2023-10-10 |  | 100%
S2460 | Review & Approve Air Duct Accessories | 30 | 25-Sep-23 A | 10-Oct-23 A | 2023-09-25 | 2023-10-10 |  | 100%
Section 23 33 19 Duct Silencers |  | 75 | 28-Sep-23 A | 29-Sep-23 A | 2023-09-28 | 2023-09-29
S2070 | Prepare & Submit Duct Silencers | 45 | 28-Sep-23 A | 29-Sep-23 A | 2023-09-28 | 2023-09-29 |  | 100%
S2080 | Review & Approve Duct Silencers | 30 | 28-Sep-23 A | 29-Sep-23 A | 2023-09-28 | 2023-09-29 |  | 100%
Section 23 34 16 Centrifugal Hvac Fans |  | 75 | 29-Sep-23 A | 12-Oct-23 A | 2023-09-29 | 2023-10-12
S2170 | Prepare & Submit Centrifugal Hvac Fans | 45 | 29-Sep-23 A | 12-Oct-23 A | 2023-09-29 | 2023-10-12 |  | 100%
S2180 | Review & Approve Centrifugal Hvac Fans | 30 | 29-Sep-23 A | 12-Oct-23 A | 2023-09-29 | 2023-10-12 |  | 100%
Section 23 34 23 Hvac Power Ventilators |  | 75 | 29-Sep-23 A | 10-Oct-23 A | 2023-09-29 | 2023-10-10
S2270 | Prepare & Submit Hvac Power Ventilators | 45 | 29-Sep-23 A | 10-Oct-23 A | 2023-09-29 | 2023-10-10 |  | 100%
S2280 | Review & Approve Hvac Power Ventilators | 30 | 29-Sep-23 A | 10-Oct-23 A | 2023-09-29 | 2023-10-10 |  | 100%
Section 23 37 00 Air Outlets And Inlets |  | 75 | 25-Sep-23 A | 26-Sep-23 A | 2023-09-25 | 2023-09-26
S2370 | Prepare & Submit Air Outlets And Inlets | 45 | 25-Sep-23 A | 26-Sep-23 A | 2023-09-25 | 2023-09-26 |  | 100%
S2380 | Review & Approve Air Outlets And Inlets | 30 | 25-Sep-23 A | 26-Sep-23 A | 2023-09-25 | 2023-09-26 |  | 100%
Section 23 57 00 Heat Exchangers For Hvac |  | 75 | 15-Sep-23 A | 21-Sep-23 A | 2023-09-15 | 2023-09-21
S2470 | Prepare & Submit Heat Exchangers For Hvac | 45 | 15-Sep-23 A | 21-Sep-23 A | 2023-09-15 | 2023-09-21 |  | 100%
S2480 | Review & Approve Heat Exchangers For Hvac | 30 | 15-Sep-23 A | 21-Sep-23 A | 2023-09-15 | 2023-09-21 |  | 100%
Section 23 62 13 Air Cooled Refrigerant Compressor And Condenser Unit |  | 45 | 02-Nov-23 A | 27-Feb-24 A | 2023-11-02 | 2024-02-27
S2030 | Prepare & Submit Air Cooled Refrigerant Compressor And Condenser Unit | 45 | 02-Nov-23 A | 21-Nov-23 A | 2023-11-02 | 2023-11-21 |  | 100%
S2040 | Review & Approve Air Cooled Refrigerant Compressor And Condenser Unit | 30 | 22-Nov-23 A | 27-Feb-24 A | 2023-11-22 | 2024-02-27 |  | 100%
Section 23 73 13 Indoor Air-Handling Units |  | 75 | 13-Sep-23 A | 10-Oct-23 A | 2023-09-13 | 2023-10-10
S2130 | Prepare & Submit Indoor Air-Handling Units | 45 | 13-Sep-23 A | 10-Oct-23 A | 2023-09-13 | 2023-10-10 |  | 100%
S2140 | Review & Approve Indoor Air-Handling Units | 30 | 13-Sep-23 A | 10-Oct-23 A | 2023-09-13 | 2023-10-10 |  | 100%
Section 23 74 13 Packaged Rooftop Units |  | 75 | 02-Nov-23 A | 22-Nov-23 A | 2023-11-02 | 2023-11-22
S2230 | Prepare & Submit Packaged Rooftop Units | 45 | 02-Nov-23 A | 22-Nov-23 A | 2023-11-02 | 2023-11-22 |  | 100%
S2240 | Review & Approve Packaged Rooftop Units | 30 | 02-Nov-23 A | 22-Nov-23 A | 2023-11-02 | 2023-11-22 |  | 100%
Section 23 81 29 Variable Refrigerant Flow Hvac Systems |  | 75 | 02-Nov-23 A | 22-Nov-23 A | 2023-11-02 | 2023-11-22
S2330 | Prepare & Submit Variable Refrigerant Flow Hvac Systems | 45 | 02-Nov-23 A | 22-Nov-23 A | 2023-11-02 | 2023-11-22 |  | 100%
S2340 | Review & Approve Variable Refrigerant Flow Hvac Systems | 30 | 02-Nov-23 A | 22-Nov-23 A | 2023-11-02 | 2023-11-22 |  | 100%
Section 23 82 00 Convection Heating And Cooling Units |  | 75 | 13-Sep-23 A | 15-Sep-23 A | 2023-09-13 | 2023-09-15
S2430 | Prepare & Submit Convection Heating And Cooling Units | 45 | 13-Sep-23 A | 15-Sep-23 A | 2023-09-13 | 2023-09-15 |  | 100%
S2440 | Review & Approve Convection Heating And Cooling Units | 30 | 13-Sep-23 A | 15-Sep-23 A | 2023-09-13 | 2023-09-15 |  | 100%
Division 26 - Electrical |  | 75 | 15-Sep-23 A | 29-Sep-23 A | 2023-09-15 | 2023-09-29
Section 26 29 23 Variable-Frequency Motor Controllers |  | 75 | 15-Sep-23 A | 29-Sep-23 A | 2023-09-15 | 2023-09-29
S1670 | Prepare & Submit Variable-Frequency Motor Controllers | 45 | 15-Sep-23 A | 29-Sep-23 A | 2023-09-15 | 2023-09-29 |  | 100%
S1680 | Review & Approve Variable-Frequency Motor Controllers | 30 | 15-Sep-23 A | 29-Sep-23 A | 2023-09-15 | 2023-09-29 |  | 100%
Procurement |  | 183 | 13-Oct-23 A | 2024-04-18 | 2023-10-13 |  | 95
S1300 | Fabricate & Deliver Radaint Runtal Baseboard-MS-1 & 2 - SRS | 40 | 13-Oct-23 A | 15-Nov-23 A | 2023-10-13 | 2023-11-15 |  | 100%
S1310 | Fabricate & Deliver EF-8, 10, 21 & 23 Samtepp | 150 | 13-Oct-23 A | 06-Jan-24 A | 2023-10-13 | 2024-01-06 |  | 100%
S1320 | Fabricate & Deliver Dampers RKB | 88 | 13-Oct-23 A | 2024-04-17 | 2023-10-13 |  | 77 | 60%
S1340 | Fabricate & Deliver UV-MS- 1-41 D&B | 55 | 13-Oct-23 A | 15-Jan-24 A | 2023-10-13 | 2024-01-15 |  | 100%
S1350 | Fabricate & Deliver HP-MS-3-9 D&B | 60 | 13-Oct-23 A | 21-Nov-23 A | 2023-10-13 | 2023-11-21 |  | 100%
S1360 | Fabricate & Deliver CV-HS-1-11 | 40 | 13-Oct-23 A | 12-Nov-23 A | 2023-10-13 | 2023-11-12 |  | 100%
S1370 | Fabricate & Deliver UH-HS-1 GC Sales | 20 | 13-Oct-23 A | 08-Nov-23 A | 2023-10-13 | 2023-11-08 |  | 100%
S1380 | Fabricate & Deliver CUH- HS-1, 2, 3 GS Sales | 40 | 13-Oct-23 A | 30-Nov-23 A | 2023-10-13 | 2023-11-30 |  | 100%
S1390 | Fabricate & Deliver radinat runtal HS R2-1, 2, 3, & 4 SRS | 40 | 13-Oct-23 A | 15-Nov-23 A | 2023-10-13 | 2023-11-15 |  | 100%
S1400 | Fabricate & Deliver F-HS-2 & 3 D&B | 150 | 13-Oct-23 A | 2024-03-01 | 2023-10-13 |  | 21 | 99%
S1410 | Fabricate & Deliver L-1 Louver with bird screen RKB | 88 | 13-Oct-23 A | 2024-04-18 | 2023-10-13 |  | 76 | 60%
S1420 | Fabricate & Deliver RTU-HS- 4 & 5 D&B | 110 | 13-Oct-23 A | 23-Feb-24 A | 2023-10-13 | 2024-02-23 |  | 100%
S1430 | Fabricate & Deliver BC-HS-1 & 2 D&B | 70 | 13-Oct-23 A | 21-Nov-23 A | 2023-10-13 | 2023-11-21 |  | 100%
S1440 | Fabricate & Deliver HC-HS-2 to 4 D&B | 40 | 13-Oct-23 A | 21-Nov-23 A | 2023-10-13 | 2023-11-21 |  | 100%
S1450 | Fabricate & Deliver AHU-HS-3 D&B | 120 | 13-Oct-23 A | 24-Jan-24 A | 2023-10-13 | 2024-01-24 |  | 100%
S1460 | Fabricate & Deliver ACCU-HS 2 D&B | 60 | 13-Oct-23 A | 01-Dec-23 A | 2023-10-13 | 2023-12-01 |  | 100%
S1470 | Fabricate & Deliver CP-HS-2 WE | 140 | 13-Oct-23 A | 05-Nov-23 A | 2023-10-13 | 2023-11-05 |  | 100%
S1480 | Fabricate & Deliver HX-HS-2 WE | 40 | 13-Oct-23 A | 02-Nov-23 A | 2023-10-13 | 2023-11-02 |  | 100%
S1490 | Fabricate & Deliver P-HS-3, 4, 5 & 6 WE | 120 | 13-Oct-23 A | 28-Nov-23 A | 2023-10-13 | 2023-11-28 |  | 100%
S1500 | Fabricate & Deliver B&G Suction Diffuser WE | 80 | 13-Oct-23 A | 05-Jan-24 A | 2023-10-13 | 2024-01-05 |  | 100%
S1510 | Fabricate & Deliver B&G Triple Duty Valve WE | 100 | 13-Oct-23 A | 06-Jan-24 A | 2023-10-13 | 2024-01-06 |  | 100%
S1520 | Fabricate & Deliver Flex Hose 6”X 24” WE | 30 | 13-Oct-23 A | 02-Nov-23 A | 2023-10-13 | 2023-11-02 |  | 100%
S1530 | Fabricate & Deliver EXP-HS-2 & 3 WE | 80 | 13-Oct-23 A | 20-Feb-24 A | 2023-10-13 | 2024-02-20 |  | 100%
S1540 | Fabricate & Deliver Flex Hose Exp Loops WE | 30 | 13-Oct-23 A | 02-Nov-23 A | 2023-10-13 | 2023-11-02 |  | 100%
S3200 | Fabricate & Deliver FT-MS-1 GC SALES | 35 | 13-Oct-23 A | 15-Nov-23 A | 2023-10-13 | 2023-11-15 |  | 100%
Construction |  | 246 | 10-Oct-23 A | 2024-09-19 | 2023-10-10 |  | 0
Mobilization |  | 10 | 10-Oct-23 A | 13-Oct-23 A | 2023-10-10 | 2023-10-13
C6920 | Mobilization & Site Prep. Mobilized demo of cielings | 10 | 10-Oct-23 A | 13-Oct-23 A | 2023-10-10 | 2023-10-13 |  | 100%
Nanuet Senior HS |  | 135 | 05-Jan-24 A | 2024-09-05 | 2024-01-05 |  | 9
Demolition |  | 14 | 2024-03-01 | 2024-03-20 |  |  | 66
C5920 | Remove Unit Ventilator - First Floor - Nanuet Senior HS | 1 | 2024-03-01 | 2024-03-01 |  |  | 64 | 0%
C7030 | Remove HVAC Ducts & Piping - Nanuet Senior HS | 14 | 2024-03-01 | 2024-03-20 |  |  | 66 | 0%
C5950 | Remove & Salvage Existing Wainscotting Pipe Enclosure - First Floor - Nanuet Senior HS | 1 | 2024-03-04 | 2024-03-04 |  |  | 64 | 0%
Basement |  | 127 | 05-Jan-24 A | 2024-06-27 | 2024-01-05 |  | 4
Architectural |  | 52 | 05-Jan-24 A | 2024-06-24 | 2024-01-05 |  | 4
C6870 | Patch Ceilings - Basement - Nanuet Senior HS | 2 | 05-Jan-24 A | 2024-06-18 | 2024-01-05 |  | 0 | 25%
C6910 | Patch Walls - Basement - Nanuet Senior HS | 3 | 2024-06-19 | 2024-06-21 |  |  | 0 | 0%
C6760 | Patch Flooring - Basement - Nanuet Senior HS | 1 | 2024-06-24 | 2024-06-24 |  |  | 4 | 0%
Mechanical |  | 125 | 11-Jan-24 A | 2024-06-27 | 2024-01-11 |  | 4
C6600 | Install Mechanical Ducts & Pipes Hangers - Basement - Nanuet Senior HS | 2 | 11-Jan-24 A | 2024-03-04 | 2024-01-11 |  | 64 | 95%
C6610 | Install HVAC Ducts & Pipes - Basement - Nanuet Senior HS | 10 | 11-Jan-24 A | 2024-03-20 | 2024-01-11 |  | 66 | 40%
C6630 | Install Above ceiling Terminal Equipment - Basement - Nanuet Senior HS | 6 | 11-Jan-24 A | 2024-03-08 | 2024-01-11 |  | 80 | 40%
C7120 | Install Mechanical Equipment - Basement - Nanuet Senior HS | 10 | 11-Jan-24 A | 2024-06-27 | 2024-01-11 |  | 4 | 95%
C6640 | Mechanical Rough-Ins Inspection - Basement - Nanuet Senior HS | 3 | 25-Jan-24 A | 2024-03-05 | 2024-01-25 |  | 81 | 95%
C6650 | Mechanical Rough-Ins Punchlist - Basement - Nanuet Senior HS | 3 | 2024-03-05 | 2024-03-08 |  |  | 81 | 0%
C6620 | Insulate HVAC Ducts & Pipes - Basement - Nanuet Senior HS | 1 | 2024-06-25 | 2024-06-25 |  |  | 4 | 0%
C6660 | Install Grilles & Difussers - Basement - Nanuet Senior HS | 2 | 2024-06-26 | 2024-06-27 |  |  | 4 | 0%
First Floor |  | 110 | 05-Jan-24 A | 2024-07-17 | 2024-01-05 |  | 0
Architectural |  | 33 | 05-Jan-24 A | 2024-07-02 | 2024-01-05 |  | 0
C6550 | Patch Ceilings - First Floor - Nanuet Senior HS | 2 | 05-Jan-24 A | 2024-06-18 | 2024-01-05 |  | 3 | 20%
C6590 | Patch Walls - First Floor - Nanuet Senior HS | 2 | 2024-06-24 | 2024-06-25 |  |  | 0 | 0%
C6440 | Patch Flooring - First Floor - Nanuet Senior HS | 5 | 2024-06-26 | 2024-07-02 |  |  | 0 | 0%
Mechanical |  | 98 | 11-Jan-24 A | 2024-07-17 | 2024-01-11 |  | 0
C6280 | Install Mechanical Ducts & Pipes Hangers - First Floor - Nanuet Senior HS | 2 | 11-Jan-24 A | 2024-03-06 | 2024-01-11 |  | 64 | 20%
C6290 | Install HVAC Ducts & Pipes - First Floor - Nanuet Senior HS | 10 | 11-Jan-24 A | 2024-03-15 | 2024-01-11 |  | 64 | 0%
C6310 | Install Above ceiling Terminal Equipment - First Floor - Nanuet Senior HS | 6 | 2024-03-06 | 2024-03-14 |  |  | 66 | 0%
C6300 | Insulate HVAC Ducts & Pipes - First Floor - Nanuet Senior HS | 1 | 2024-03-15 | 2024-03-18 |  |  | 64 | 0%
C6320 | Mechanical Rough-Ins Inspection - First Floor - Nanuet Senior HS | 2 | 2024-03-18 | 2024-03-20 |  |  | 64 | 0%
C6330 | Mechanical Rough-Ins Punchlist - First Floor - Nanuet Senior HS | 3 | 2024-03-20 | 2024-03-25 |  |  | 64 | 0%
C6340 | Install Grilles & Difussers - First Floor - Nanuet Senior HS | 1 | 2024-03-25 | 2024-03-26 |  |  | 70 | 0%
C7100 | Install Mechanical Equipment - First Floor - Nanuet Senior HS | 10 | 2024-07-03 | 2024-07-17 |  |  | 0 | 0%
Second Floor |  | 88 | 05-Jan-24 A | 2024-07-16 | 2024-01-05 |  | 46
Architectural |  | 29 | 05-Jan-24 A | 2024-06-25 | 2024-01-05 |  | 59
C6230 | Patch Ceilings - Second Floor - Nanuet Senior HS | 2 | 05-Jan-24 A | 2024-06-19 | 2024-01-05 |  | 36 | 20%
C6270 | Patch Walls - Second Floor - Nanuet Senior HS | 3 | 2024-06-19 | 2024-06-24 |  |  | 59 | 0%
C6120 | Patch Flooring - Second Floor - Nanuet Senior HS | 1 | 2024-06-24 | 2024-06-25 |  |  | 59 | 0%
Mechanical |  | 76 | 11-Jan-24 A | 2024-07-16 | 2024-01-11 |  | 46
C5960 | Install Mechanical Ducts & Pipes Hangers - Second Floor - Nanuet Senior HS | 1 | 11-Jan-24 A | 2024-04-01 | 2024-01-11 |  | 4 | 10%
C7110 | Install Mechanical Equipment - Second Floor - Nanuet Senior HS | 4 | 11-Jan-24 A | 2024-04-01 | 2024-01-11 |  | 4 | 85%
C5970 | Install HVAC Ducts & Pipes - Second Floor - Nanuet Senior HS | 10 | 2024-06-19 | 2024-07-03 |  |  | 36 | 0%
C5990 | Install Above ceiling Terminal Equipment - Second Floor - Nanuet Senior HS | 6 | 2024-06-19 | 2024-06-27 |  |  | 40 | 0%
C5980 | Insulate HVAC Ducts & Pipes - Second Floor - Nanuet Senior HS | 1 | 2024-07-03 | 2024-07-05 |  |  | 36 | 0%
C6000 | Mechanical Rough-Ins Inspection - Second Floor - Nanuet Senior HS | 3 | 2024-07-05 | 2024-07-10 |  |  | 36 | 0%
C6010 | Mechanical Rough-Ins Punchlist - Second Floor - Nanuet Senior HS | 3 | 2024-07-10 | 2024-07-15 |  |  | 36 | 0%
C6020 | Install Grilles & Difussers - Second Floor - Nanuet Senior HS | 1 | 2024-07-15 | 2024-07-16 |  |  | 45 | 0%
Roof |  | 85 | 15-Jan-24 A | 2024-04-05 | 2024-01-15 |  | 107
Structural |  | 5 | 15-Jan-24 A | 2024-03-11 | 2024-01-15 |  | 14
C5840 | Install New Roof Steel Framing for Mechanical Equipment - Roof - Nanuet Senior HS | 5 | 15-Jan-24 A | 2024-03-11 | 2024-01-15 |  | 14 | 85%
Mechanical |  | 85 | 15-Jan-24 A | 2024-04-05 | 2024-01-15 |  | 107
C5880 | Install New Mechanical Equipment Curbs Equipment Rails & Pitch Pockets - Roof - Nanuet Senior HS | 4 | 15-Jan-24 A | 2024-03-15 | 2024-01-15 |  | 21 | 80%
C7130 | Install ACCU-HS-2 - Roof - Nanuet Senior HS | 12 | 15-Jan-24 A | 2024-03-15 | 2024-01-15 |  | 120 | 90%
C5870 | Remove Roof Top Exhaust Fan & All Associated Controls & Wiring - Roof - Nanuet Senior HS | 5 | 2024-04-01 | 2024-04-05 |  |  | 0 | 0%
C7090 | Install RTUs 4,5 - Roof - Nanuet Senior HS (Crane Pick) | 3 | 2024-04-01 | 2024-04-03 |  |  | 0 | 0%
C7190 | Install RTUs 4,5 - Roof - Nanuet Senior HS (RTU Connections) | 5 | 2024-04-01 | 2024-04-05 |  |  | 0 | 0%
Testing & Commissioning |  | 46 | 2024-07-04 | 2024-09-05 |  |  | 9
A1000 | Install Mechanical Controls - Nanuet Senior HS | 34 | 2024-07-04 | 2024-08-20 |  |  | 0 | 0%
A1010 | Point-To-Point checks - Nanuet Senior HS | 15 | 2024-08-01 | 2024-08-21 |  |  | 10 | 0%
TC100 | HVAC Testing & Balancing - Nanuet Senior HS | 5 | 2024-08-21 | 2024-08-28 |  |  | 9 | 0%
TC110 | HVAC Commissioning - Nanuet Senior HS | 5 | 2024-08-28 | 2024-09-05 |  |  | 9 | 0%
Barr MS |  | 210 | 05-Jan-24 A | 2024-09-19 | 2024-01-05 |  | 0
Demolition |  | 14 | 2024-07-05 | 2024-07-24 |  |  | 20
C6950 | Remove Unit Ventilators - Barr MS | 2 | 2024-07-05 | 2024-07-08 |  |  | 12 | 0%
C6960 | Remove Casework - Barr MS | 1 | 2024-07-09 | 2024-07-09 |  |  | 12 | 0%
C6970 | Remove Portion of Existing VAT Flooring - Barr MS Asbestos Subcontractor | 6 | 2024-07-10 | 2024-07-17 |  |  | 12 | 0%
C7020 | Remove HVAC Ducts & Pipes & Piping - Barr MS | 11 | 2024-07-10 | 2024-07-24 |  |  | 20 | 0%
Asbestos Abatement Barr MS |  | 3 | 2024-07-15 | 2024-07-17 |  |  | 12
C1010 | Perform Asbestos Abatement @ First Floor - Barr MS | 3 | 2024-07-15 | 2024-07-17 |  |  | 12 | 0%
C1020 | Perform Asbestos Abatement @ Second Floor - Barr MS | 3 | 2024-07-15 | 2024-07-17 |  |  | 12 | 0%
Lower Level/Basement |  | 5 | 2024-07-18 | 2024-07-24 |  |  | 23
Architectural |  | 5 | 2024-07-18 | 2024-07-24 |  |  | 23
C5170 | Patch Floor - Lower Level - Barr MS | 5 | 2024-07-18 | 2024-07-24 |  |  | 23 | 0%
C5280 | Patch Ceilings - Lower Level - Barr MS | 5 | 2024-07-18 | 2024-07-24 |  |  | 23 | 0%
C5320 | Patch Walls - Lower Level - Barr MS | 5 | 2024-07-18 | 2024-07-24 |  |  | 23 | 0%
First Floor |  | 106 | 08-Jan-24 A | 2024-08-19 | 2024-01-08 |  | 22
Architectural |  | 106 | 08-Jan-24 A | 2024-08-19 | 2024-01-08 |  | 22
C4070 | Patch Ceilings - First Floor - Barr MS | 2 | 08-Jan-24 A | 2024-07-24 | 2024-01-08 |  | 26 | 45%
C4080 | Install Casework - First Floor - Barr MS | 1 | 2024-07-25 | 2024-07-25 |  |  | 39 | 0%
C4140 | Patch Walls - First Floor - Barr MS | 3 | 2024-08-09 | 2024-08-13 |  |  | 12 | 0%
C3720 | Patch Flooring - First Floor - Barr MS | 4 | 2024-08-14 | 2024-08-19 |  |  | 12 | 0%
Mechanical |  | 16 | 2024-07-18 | 2024-08-08 |  |  | 12
C3730 | Install Mechanical Ducts & Pipes Hangers - First Floor - Barr MS | 1 | 2024-07-18 | 2024-07-18 |  |  | 12 | 0%
C3750 | Install HVAC Ducts & Pipes - First Floor - Barr MS | 12 | 2024-07-18 | 2024-08-02 |  |  | 12 | 0%
C3760 | Install Above ceiling Terminal Equipment & Unit Ventilator 15 - First Floor - Barr MS | 4 | 2024-07-19 | 2024-07-24 |  |  | 15 | 0%
C3800 | Insulate HVAC Ducts & Pipes - First Floor - Barr MS | 1 | 2024-07-24 | 2024-07-24 |  |  | 15 | 0%
C3870 | Mechanical Rough-Ins Inspection - First Floor - Barr MS | 2 | 2024-07-25 | 2024-07-26 |  |  | 15 | 0%
C3880 | Mechanical Rough-Ins Punchlist - First Floor - Barr MS | 2 | 2024-07-29 | 2024-07-30 |  |  | 15 | 0%
C4090 | Install Grilles & Difussers - First Floor - Barr MS | 4 | 2024-08-05 | 2024-08-08 |  |  | 12 | 0%
Second Floor |  | 34 | 05-Jan-24 A | 2024-09-03 | 2024-01-05 |  | 12
Architectural |  | 28 | 05-Jan-24 A | 2024-09-03 | 2024-01-05 |  | 12
C4780 | Patch Ceiling - Second Floor - Barr MS | 6 | 05-Jan-24 A | 2024-08-19 | 2024-01-05 |  | 12 | 5%
C4890 | Patch Walls - Second Floor - Barr MS | 4 | 08-Jan-24 A | 2024-08-19 | 2024-01-08 |  | 12 | 45%
C4900 | Install Casework - Second Floor - Barr MS | 1 | 2024-07-26 | 2024-07-26 |  |  | 39 | 0%
C4830 | Patch Flooring - Second Floor - Barr MS | 10 | 2024-08-20 | 2024-09-03 |  |  | 12 | 0%
Mechanical |  | 13 | 2024-07-18 | 2024-08-05 |  |  | 12
C4540 | Install Mechanical Ducts & Pipes Hangers - Second Floor - Barr MS | 1 | 2024-07-18 | 2024-07-18 |  |  | 12 | 0%
C4550 | Install HVAC Ducts & Pipes - Second Floor - Barr MS | 8 | 2024-07-18 | 2024-07-29 |  |  | 16 | 0%
C4570 | Install Above ceiling Terminal Equipment & unit Ventilator 24 - Second Floor - Barr MS | 4 | 2024-07-19 | 2024-07-24 |  |  | 12 | 0%
C4560 | Insulate HVAC Ducts & Pipes - Second Floor - Barr MS | 1 | 2024-07-24 | 2024-07-24 |  |  | 12 | 0%
C4580 | Mechanical Rough-Ins Inspection - Second Floor - Barr MS | 2 | 2024-07-25 | 2024-07-26 |  |  | 12 | 0%
C4590 | Mechanical Rough-Ins Punchlist - Second Floor - Barr MS | 3 | 2024-07-29 | 2024-07-31 |  |  | 12 | 0%
C4600 | Install Grilles & Difussers - Second Floor - Barr MS | 3 | 2024-08-01 | 2024-08-05 |  |  | 12 | 0%
Roof |  | 41 | 05-Jan-24 A | 2024-04-02 | 2024-01-05 |  | 100
Structural |  | 4 | 05-Jan-24 A | 2024-04-02 | 2024-01-05 |  | 14
C1030 | Install New Roof Framing for Mechanical Equipment - Roof - Barr MS | 4 | 05-Jan-24 A | 2024-04-02 | 2024-01-05 |  | 14 | 0%
Mechanical |  | 41 | 05-Jan-24 A | 23-Jan-24 A | 2024-01-05 | 2024-01-23
C5770 | Remove Roof Top Exhaust Fan & All Associated Controls & Wiring - Roof - Barr MS | 14 | 05-Jan-24 A | 16-Jan-24 A | 2024-01-05 | 2024-01-16 |  | 100%
S2980 | Install HP-MS-3-9 - Roof - Barr MS | 17 | 05-Jan-24 A | 16-Jan-24 A | 2024-01-05 | 2024-01-16 |  | 100%
C7140 | Install New Mechanical Equipment - Roof - Barr MS | 17 | 05-Jan-24 A | 23-Jan-24 A | 2024-01-05 | 2024-01-23 |  | 100%
S2940 | Install EF-8, 10, 21 & 23 - Roof - Barr MS | 17 | 11-Jan-24 A | 16-Jan-24 A | 2024-01-11 | 2024-01-16 |  | 100%
Testing & Commissioning - Barr MS |  | 56 | 2024-07-04 | 2024-09-19 |  |  | 0
A1020 | Install Mechanical Controls - Barr MS | 40 | 2024-07-04 | 2024-08-28 |  |  | 0 | 0%
A1030 | Point-To-Point checks - Barr MS | 15 | 2024-08-01 | 2024-08-21 |  |  | 0 | 0%
TC120 | HVAC Testing & Balancing - Barr MS | 10 | 2024-08-21 | 2024-09-05 |  |  | 0 | 0%
TC130 | HVAC Commissioning - Barr MS | 10 | 2024-09-05 | 2024-09-19 |  |  | 0 | 0%
Close Outs |  | 27 | 2024-09-19 | 2024-10-29 |  |  | 0
CLO100 | Final Inspections | 6 | 2024-09-19 | 2024-09-27 |  |  | 0 | 0%
CLO110 | Punchlist | 10 | 2024-09-27 | 2024-10-11 |  |  | 0 | 0%
CLO120 | Final Clean Up | 6 | 2024-10-11 | 2024-10-22 |  |  | 0 | 0%
CLO130 | Demobilization | 5 | 2024-10-22 | 2024-10-29 |  |  | 0 | 0%